## works
WORKS
BUDGET PERIOD |  | 2021 |  |  |  | Tender Document | Tendering Period |  | Tender evaluation |  | Contract finalization |  |  | Contract Implementation
SOURCE OF FUND:DACF/RFG- DACF |  |  | BASIC DATA
Contract Package | Plan vs. Actual | Package Number | Estimated Amount (Ghana Cedis) | Procurement Method | Final Authority for Contract Award | Prep & Submission by Ex Agency | Invitation Date | Tender Closing /Opening Date | SubmissionTender Eval.Rpt | Approval by Final Authority | Contract Amount (Ghana Cedis) | Date Contract award | Date Contract Signature | Mobilization advance payment | Substantial Completion | Final Acceptance | Final Cost (Ghana Cedis)
| Duration |  |  |  |  | 2-4 wks | 1-2 wks | 4-13 wks | 2-3 wks | 1 wk |  | 1 wk | 1-2 wks | 2 wks | 4-6 MTHS | 6 MTHS
Construction of semi detached 2-bed room for staff | plan | AYDA/WKS/DACF/2021/01 | 410362 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 410362 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Self-help community initiated projects in the district | plan | AYDA/WKS/DACF/2021/02 | 255181 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 255181 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Repairs and maintenance of offices,& residential buildings and general equipment | plan | AYDA/WKS/DACF/2021/03 | 17000 | P.Q | HoE | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 17000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Drill and construct boreholes in the district | plan | AYDA/WKS/DACF/2021/04 | 250000 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 250000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Maintenance ,rehabilitation,refurbishment and upgrading of existing assets-feeder roads | plan | AYDA/WKS/DACF/2021/05 | 200000 | P.Q | HoE | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 200000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Maintenace of broken down boreholes in the district | plan | AYDA/WKS/IGF/2021/06 | 127918 | P.Q | HoE | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 127918 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Construction of 10-seater KVIP at Kuano | plan | AYDA/WKS/DACF/2021/07 | 230000 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 230000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Completion of DCE bungalow at Coaltar | plan | AYDA/WKS/DACF/2021/08 | 127487.48 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 127487.48 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Completion of market Shed at Dokrochiwa | plan | AYDA/WKS/DACF/2021/09 | 19961.78 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 19961.78 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Completion of ICT centre at Mfranta | plan | AYDA/WKS/RFG-DACF/2021/10 | 38841.11 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 38841.11 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
EDUCATION
Construction of 1no. 6 unit classroom block at Yaw Boame | plan | AYDA/WKS/DACF/2021/11 | 300000 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 300000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Construction of 1No. 3 units JHS classroom block with staff room ,store &office at Amanase Homesu (MTN) | plan | AYDA/WKS/DACF/2021/12 | 240000 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 240000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Construction of 2No.2 units KG blocks and ancillary facilities at Kwaboanta and Anum | plan | AYDA/WKS/DACF/2021/13 | 390000 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 390000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Rehabilitation of 1NO.6 units classroom block with store and office at Ntowkrom | plan | AYDA/WKS/DACF-RFG/2021/14 | 197103 | P.Q | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 197103 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Rehabilitation of 1NO.6 units classroom block at Govinakrom | plan | AYDA/WKS/DACF/2021/15 | 80000 | P.Q | HoE | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 80000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Completion of 1No. 3 units classroom block with staff room ,office & store at Kraboa | plan | AYDA/WKS/DACF/2021/16 | 198712 | P.Q | HoE | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 198712 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Completion of 1No. CHPS compound with 10000 litres polytank & Nurses accommodation at Krabokese | plan | AYDA/WKS/DACF/2021/17 | 62226.16 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 62226.16 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Completion of 2No. CHPS compounds with mechanized boreholes and single rooms at Sowatey and Kuano | plan | AYDA/WKS/2021/18 | 410000 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 410000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Rehabilitation of CHPS compound at Anum Apapam | plan | AYDA/WKS/DACF/2021/19 | 72072.4 | P.Q | HoE | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 72072.4 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Rehabilitation of Teacher Mante market | plan | AYDA/WKS/DACF/2021/20 | 80000 | P.Q | HoE | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 80000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Rehabilitation of existing toilets in the district | plan | AYDA/WKS/DACF/2021/19 | 250000 | NCT | ETC | 2021-06-01 | 13/1/2021 | 27/1/2021 | 2021-03-02 | 2021-10-02 | 250000 | 17/2/2021 | 24/2/2021 | 2021-09-03 | 15/7/2021 | 18/7/2021
actual
Total | plan |  | 3956864.93 | [7 empty] | 3956864.93
actual

## goods
Procurement Entity | [6 empty] | GOODS
budget Period |  | 2021
source of Funding |  | Z | BASIC DATA Tendering Period Tender Evaluation Contract Finalization Goods Delivery
Contract Package | Plan Vs Actual | Package Number | Estimated Amount (Ghana Cedis) | Procurement Method | Final Authority for Contract Award | Prep & Submission | Tender Invitation Date | Tender Closing | Submission of Tender Eval Report | Approval by Final Authority | Contract Amount (Ghana Cedis) | Date Contract Award | Date Contract Signature | Arrival of Goods | Inspection Final Acceptance
| Duration |  |  |  |  | 3-6 wks | 1-2 wks | 4-12 wks | 2-3 wks | 2 wks |  | 2 wks | 1 wk | 1-2wks | 1 wk
CENTRAL ADMIN.
Procure office supplies and consumables | plan | AYDA/GDS/DACF/2021/01 | 66000 | P.Q | HoE | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 66000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
Procure office logistics for decentralised departments | plan | AYDA/GDS/IGF/2021/02 | 20000 | P.Q | HoE | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 20000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
Procure equipments ,plants,furniture and fittings (laptops,printers,chairs etc) | plan | AYDA/GDS/IGF/2021/03 | 120000 | P.Q | ETC | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 120000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
Procure living room items (furniture,equipment,consumables, etc)to furnish DCE's Bungalow | plan | AYDA/GDS/IGF/2021/04 | 100000 | P.Q | ETC | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 100000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
Procure petty tools and implements | plan | AYDA/GDS/DACF/2021/05 | 100000 | P.Q | ETC | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 100000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
EDUCATION
Procure dual and mono desks | plan | AYDA/GDS/DACF/2021/06 | 100000 | P.Q | ETC | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 100000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
HEALTH
Procure Sanitary materials-COVID-19 | plan | AYDA/GDS/DACF/2021/07 | 15000 | P.Q | HoE | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 15000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
Procure nose masks and veronica buckets-COVID-19 | plan | AYDA/GDS/DACF/2021/08 | 35000 | P.Q | HoE | 13/1/2021 | 2021-03-02 | 17/02/2021 | 2021-02-03 | 16/03/2021 | 35000 | 30/03/2021 | 2021-06-04 | 20/04/2021 | 27/04/2021
actual
| plan |  | 556000 | [7 empty] | 556000
actual

## c serv.
PROCUREMENT ENTITY | [6 empty] | TECHNICAL/CONSULTANCY SERVICES
BUDGET PERIOD |  | 2021 |  |  |  | Preparation of Request for Proposals | [6 empty] | Negotiation |  | Contract Finalization
SOURCE OF FUND |  |  | BASIC DATA | [13 empty] | Contract implementation
Contract Package | Plan Vs Actual | Package Number | Estimated Amount (Ghana Cedis) | Procure-ment Method | Final Authority for Contract Award | Prep & Submission by Ex Agency | Invitation Date | Submission /Opening Date | Complete Eval Report ( T ) | Opening Financial Proposals | Complete Eval.Report ( T ) ( F ) | Approval of Eval. Report ( T ) ( F) | Negotiation | Approval of Negotiation Report | Date Contract award | Date Contract Signature | Mobilization advance payment | Final Report
| Duration |  |  |  |  | 3-6 wks | 1-2 wks | 4-12 wks | 2-3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 1-2 wks | 1 wk |  | 2 wks
CENTRAL ADMIN.
Manpower and skill development-capacity building | plan | AYDA/TS/DACF/2021/01 | 120296 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
Development and management of database | plan | AYDA/TS/DACF/2021/02 | 31437 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
FINANCE
Maintenance of official vehicles | plan | AYDA/TS/DACF/2021/03 | 60000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
Carry out data collection and exercise and update of revenue database | plan | AYDA/TS/DACF/2021/04 | 34545 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
Waste management services | plan | AYDA/TS/DACF/2021/05 | 105000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
PHYSICAL PLANNING DEPT
Street naming/property addressing exercise | plan | AYDA/TS/DACF/2021/06 | 60000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
Preparation of planning schemes for the district | plan | AYDA/TS/DACF/2021/07 | 20000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
AGRIC
Train women groups in dynamics and entrepreneurial skills | plan | AYDA/TS/DACF/2021/08 | 20000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
Technical and vocational training | plan | AYDA/TS/DACF/2021/09 | 170000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
ENVIRONMENTAL
Evacuation of refuse dumps in the (pushing and levelling) | plan | AYDA/TS/DACF/2021/10 | 100000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
Fumigation services | plan | AYDA/TS/DACF/2021/11 | 161000 | QBS |  | 15/1/21 | 2021-05-02 | 19/2/21 | 4/3/21 | 18/3/21 | 1/4/21 | 15/4/21 | 31/5/21 | 14/6/21 | 21/6/21 | 28/6/21 | 19/10/21 | 2/11/21
actual
TOTAL | plan |  | 882278
actual

## t serv.
PROCUREMENT ENTITY | [6 empty] | TECHNICAL SERVICE
BUDGET PERIOD |  | 2020 |  |  |  | Preparation of Request for Proposals | [6 empty] | Negotiation |  | Contract Finalization
SOURCE OF FUND |  |  | BASIC DATA | [13 empty] | Contract implementation
Contract Package | Plan Vs Actual | Package Number | Estimated Amount (Ghana Cedis) | Procure-ment Method | Final Authority for Contract Award | Prep & Submission by Ex Agency | Invitation Date | Submission /Opening Date | Complete Eval Report ( T ) | Opening Financial Proposals | Complete Eval.Report ( T ) ( F ) | Approval of Eval. Report ( T ) ( F) | Negotiation | Approval of Negotiation Report | Date Contract award | Date Contract Signature | Mobilization advance payment | Final Report
| Duration |  |  |  |  | 3-6 wks | 1-2 wks | 4-12 wks | 2-3 wks | 2 wks | 2 wks | 2 wks | 2 wks | 2 wks | 1-2 wks | 1 wk |  | 2 wks
| plan |  |  |  |  | 15/1/20 | 2020-05-02 | 19/2/20 | 4/3/20 | 18/3/20 | 1/4/20 | 15/4/20 | 29/5/20 | 13/6/20 | 20/6/20 | 27/6/20 | 19/10/20 | 2/11/20
actual
| plan |  |  |  |  | 15/1/20 | 2020-05-02 | 19/2/20 | 4/3/20 | 18/3/20 | 1/4/20 | 15/4/20 | 29/5/20 | 13/6/20 | 20/6/20 | 27/6/20 | 19/10/20 | 2/11/20
actual
plan
actual
plan
actual
plan
actual