COMPOSITE ANNUAL ACTION PLAN OF AYENSUANO DISTRICT ASSEMBLY FOR 2022

| Development Dimension: Governance, Corruption and Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | Programmes | Sub-Programmes | Projects /Activities (Operations) | Location | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Programme status |  | Implementing Agencies |  |
|  |  |  |  |  | 1ST | 2ND | 3RD | 4TH | GOG |  | IGF | Donor | New | Ongoing | Lead | Collaborating |
|  |  |  |  |  |  |  |  |  | DACF | DDF |  |  |  |  |  |  |
| 1 | Management and Administration | Planning, Budgeting and Coordination | Organize quarterly public forum on the implementation of 2022 AAP and Budget | Coaltar |  |  |  |  | 10,000 |  |  |  |  |  | Central Administraion | DPCU members, Stakeholders, Assembly members |
| 2 | Management and Administration | Planning, Budgeting and Coordination | Organize mid and annual performance review meetings on the implementation of 2022 AAP and Composite Budget | Coaltar |  |  |  |  | 15,000 |  |  |  |  |  | Central Administraion | DPCU members, Stakeholders, Assembly members, NGOs, ERCC |
| 3 | Management and Administration | Human Resource Management | Support staff on capacity building programme | Coaltar, Accra |  |  |  |  | 20,000 |  |  |  |  |  | Central Administraion | AyDA, Staff, Training Institutions, Consultants |
| 4 | Management and Administration | Planning, Budgeting and Coordination | Carry out monitoring on Development projects and Programmes with stakeholders | District wide |  |  |  |  | 20,000 |  |  |  |  |  | Central Administraion | DPCU members, Stakeholders, A/Ms Contractors, Area Council Executives |
| 5 | Management and Administration | General Administration | Organize quarterly meetings of the Assembly | Coaltar |  |  |  |  | 25,000 |  |  |  |  |  | Central Administraion | DPCU members, Sub-C’ttee and Executive C’ttee Members |
| 6 | Management and Administration | Planning, Budgeting and Coordination | Prepare 2023 District Composite Budget | Coaltar |  |  |  |  | 20,000 |  |  |  |  |  | Central Administraion | DPCU members, Stakeholders, Assembly members |
| 7 | Management and Administration | General Administration | Organize and Support National Celebrations in the District (i.e. Independence day, May Day, etc) | District wide |  |  |  |  | 30,000 |  |  |  |  |  | Central Administraion | Assembly members, community members |
| 8 | Management and Administration | General Administration | Provide Logistics and financial support to the Departments of the Assembly in the district | Coaltar |  |  |  |  | 25,000 |  |  |  |  |  | Central Administraion | HoDs, PO, DFO |
| 9 | Management and Administration | General Administration | Procure 1No. Motor bike for the Assembly | Accra/ Koforidua |  |  |  |  | 8,000 |  |  |  |  |  | Central Administraion | PO, TO, Tender C’ttee, Suppliers |
| 10 | Management and Administration | Finance and Revenue Mobilization | Carryout maintenance on 4No. official Vehicles | Accra/ Koforidua |  |  |  |  | 20,000 |  |  |  |  |  | Central Administraion | AyDA, T/O Drivers, Mechanics |
| 11 | Management and Administration | General Administration | Procure 3No. Laptops and 2No. Desktops for official use | Accra/ Koforidua |  |  |  |  | 12,000 |  |  |  |  |  | Central Administraion | AyDA, P/O, Tender C’ttee, Suppliers |
| 12 | Infrastructure Delivery and management | Infrastructure Development | Construction of 1No. Area Council office | Asuboi |  |  |  |  |  |  | 150,000 |  |  |  | DWD | AyDA, Area Councils executives, Chiefs,A/M, Contractors |
| 13 | Management and Administration | General Administration | Procure Furniture and Curtains to furnish Assembly Hall and offices | Accra/ Koforidua |  |  |  |  |  |  | 44,500 |  |  |  | Central Administraion | AyDA, P/O, Tender C’ttee, suppliers |
| 14 | Infrastructure delivery and Management | Infrastructure Development | Carry out extension of streetlights and replacement of street light bulbs in the District | District wide |  |  |  |  | 20,000 |  |  |  |  |  | Phyical Planning Dept. | Assembly and unit C’ttee members, Trad. Auth., MP, NGOs, Community members. |
| Development Dimension: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programmes | Sub-Programmes | Projects /Activities (Operations) | Location | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Programme Status |  | Implementing Agencies |  |
|  |  |  |  |  | 1ST | 2ND | 3RD | 4TH | GOG |  | IGF | Donor | New | Ongoing | Lead | Collaborating |
|  |  |  |  |  |  |  |  |  | DACF | DDF |  |  |  |  |  |  |
| 15 | Management and Administration | Finance and revenue mobilization | Carry out data collection exercise and update of the District’s revenue database | District wide |  |  |  |  | 20,000 |  |  |  |  |  | Finance Dept. | AyDA, Revenue collectors, Assembly and unit committee members |
| 16 | Economic Development | Agriculture Development | Establish Demonstration farms at the three Area Councils | Coaltar, Anum Apapam, Asuboi |  |  |  |  |  |  |  | 3,000 |  |  | Agric Dept | AyDA, MoFA, Farmers, NGOs, FBOs |
| 17 | Economic Development | Agriculture Development | Organise RELC planning sessions for stakeholders | Coaltar, |  |  |  |  |  |  |  | 5,000 |  |  | Agric Dept. | AyDA, MoFA, Farmers, NGOs, FBOs, Researchers |
| 18 | Economic Development | Agriculture Development | Support PFJ programme in the District to achieve One District one exportable crop/ factory | District wide |  |  |  |  | 10, 000 |  |  |  |  |  | Agric Dept | AyDA, MoFA, Farmers, NGOs, FBOs, Extension Officers |
| 19 | Economic Development | Agriculture Development | Provide Direct extension services to farmers and FBOs by AEAS | District wide |  |  |  |  |  |  |  | 3,000 |  |  | Agric Dept. | AyDA, MoFA, Farmers, NGOs, FBOs, Extension Officers |
| 20 | Economic Development | Agriculture Development | Construct two tonner improved narrow ventilated maize crib for adoption by 100 farmers | Asuboi, Coaltar |  |  |  |  |  |  |  | 10,000 |  |  | Agric Dept | AyDA, MoFA, Farmers, NGOs, FBOs |
| 21 | Economic Development | Agriculture Development | Form sustainable value chain farmer groups to access local and international Markets | District wide |  |  |  |  |  |  | 1,500 |  |  |  | Agric Dept. | AyDA, MoFA, Farmers, NGOs, FBOs |
| 22 | Economic Development | Agriculture Development | Organize farmers day celebration in the district | Coaltar |  |  |  |  | 20,000 |  |  |  |  |  | Agric Dept. | AyDA, Chiefs, A/Ms,NGOs, Farmers, General Public |
| Development Dimension: Social Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programmes | Sub-Programmes | Projects /Activities (Operations) | Location | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Programme status |  | Implementing Agencies |  |
|  |  |  |  |  | 1ST | 2ND | 3RD | 4TH | GOG |  | IGF | Donor | New | Ongoing | Lead | Collaborating |
|  |  |  |  |  |  |  |  |  | DACF | DDF |  |  |  |  |  |  |
| 23 | Infrastructure Delivery and Management | Infrastructure Development | Construct 1No. 6-units classroom block | Owusu Wawase |  |  |  |  | 350,00 |  |  |  |  |  | DWD | AyDA, GET Fund, MLGRD,DDF, Community, GES |
| 24 | Infrastructure Delivery and Management | Infrastructure Development | Rehabilitate 1No. 6-units classroom block | Budu |  |  |  |  | 150,000 |  |  |  |  |  | DWD | AyDA, GET Fund, MLGRD,DDF, Community, GES |
| 25 | Infrastructure Delivery and Management | Infrastructure Development | Construct 1No. 3- units JHS classroom block | Otoase D/A JHS |  |  |  |  | 220,000 |  |  |  |  |  | DWD | AyDA, GET Fund, MLGRD,DDF, Community, GES |
| 26 | Infrastructure Delivery and Management | Infrastructure Development | Rehabilitate 1No. 3- units classroom block | Govina-krom D/A |  |  |  |  | 120,000 |  |  |  |  |  | DWD | AyDA, GETFund, Contractor, consultant, Community, GES |
| 27 | Infrastructure Delivery and Management | Infrastructure Development | Construct 3No. 2- units K.G block and ancillary facilities | Anum Apapam D/A School, Teacher Mante, Kwaboan-ta Jn. |  |  |  |  | 200,000 |  |  |  |  |  | DWD | GET Fund, MLGRD,DDF, Community, GES |
| 28 | Social Service Delivery | Education and Youth Development | Support needy but brilliant students in the District | District wide |  |  |  |  |  |  | 74, 170 |  |  |  | GES | A/Ms, Circuit Supervisors, Headteachers, SMCs |
| 29 | Social Service Delivery | Education and Youth Development | Support STMIE Clinic activities in the District | District wide |  |  |  |  |  |  | 9,000 |  |  |  | GES | AyDA, PTAs/SMCs, pupils, Parents |
| 30 | Social Service Delivery | Education and Youth Development | Facilitate to expand School the Feeding Programme | District wide |  |  |  |  |  |  | 10,000 |  |  |  | GES | AyDA, MGCSP, DHA, PTAs/SMCs, |
| 31 | Social Service Delivery | Health Delivery | Construct 1No. CHPs compound with mechanized borehole and 2 Single rooms for health attendants | Obuoho Nyarko |  |  |  |  | 230,000 |  |  |  |  |  | DWD | AyDA, Dist. Health Admin, Community members, Assembly & Unit committee members, Contractors |
| 32 | Social Service Delivery | Health Delivery | Register 1000 persons above 70 years under free NHIS | District wide |  |  |  |  |  |  | 6,000 |  |  |  | Dept of Soc. Dev’t | AyDA, NCCE, NGOs, MP, Aged, CHRAJ, Chiefs |
| 33 | Social Service Delivery | Health Delivery | Support HIV/AIDS activities in the District | District wide |  |  |  |  |  |  | 18,542 |  |  |  | DHA | GAC, FP, NGOs, Health workers, Gen. public, |
| 34 | Social Service Delivery | Health Delivery | Support DHA on malaria programs in the District | District wide |  |  |  |  |  |  | 15,000 |  |  |  | DHA | GHS, Gen. public, Health workers |
| 35 | Infrastructure Delivery and Management | Infrastructure Development | Drill and Construct 2No. boreholes in the District | Abeasi, Govina-krom, |  |  |  |  |  |  | 56,000 |  |  |  | DWD | AyDA, NGOs, Community members, Assembly &Unit Committee members, WATSANC, |
| 36 | Infrastructure Delivery and Management | Infrastructure Development | Rehabilitate 5No. boreholes in the District | Agboja |  |  |  |  |  | 75,000 |  |  |  |  | DWD | AyDA, NGOs, Community members, Assembly &Unit C’ttee members, WATSANC, Contractors |
| 37 | Environmental and sanitation Management | Natural Resource Conservation | Evacuate refuse dumps in the District | Coatar, Amanase, Krabo-kese |  |  |  |  | 320, 000 |  |  |  |  |  | DEHU | AyDA, Zoomlion, Traditional Authorities |
| 38 | Infrastructure Delivery and Management | Infrastructure Development | Construct 12 Seater W/C toilet facility | Coaltar |  |  |  |  | 230, 000 |  |  |  |  |  | DWD | AyDA, DEHU, Chiefs, Contractors |
| 39 | Economic Development | Trade, tourism and industrial development | Construct 100-units markets stalls, urinal and warehouse | Ayeko-kooso |  |  |  |  | 200,000 |  |  |  |  |  | DWD | AyDA, Chiefs, Assembly members, traders, Contractors |
| 40 | Social Service Delivery | Social welfare and community development | Organise workshop on effective participation in decision making for women | Coaltar |  |  |  |  | 5,000 |  |  |  |  |  | Dept. of Soc. Dev’t | AyDA, NGOs, women groups, ISD, NCCE |
| 41 | Management and Administration | Human Resource Management | Support the Nations Builders Corps (NaBCO) programme in the District | Coaltar |  |  |  |  | 10,000 |  |  |  |  |  | Central Administraion | AyDA, |
| 43 | Social Service Delivery | Social welfare and community development | Train 10 women Groups in group dynamics, entrepreneurial skills, home management and records keeping | Coaltar |  |  |  |  |  |  | 10,000 |  |  |  | Dept. of Soc. Dev’t | AyDA, NBSSI, NGOs, Women groups , trainers |
| 44 | Social Service Delivery | Social welfare and community development | Train women groups in tye and dye and soap making | District wide |  |  |  |  |  |  | 10,000 |  |  |  | Dept. of Soc. Dev’t | AyDA, NBSSI, NGOs, women groups , trainers |
| 45 | Social Service Delivery | Social welfare and community development | Support LEAP Programme in the District | District wide |  |  |  |  | 15,000 |  |  |  |  |  | Dept. of Soc. Dev’t | AyDA, MGCSP, Assembly members, Traditional Authorities, Aged, CLIC Members, ISD |
| 46 | Social Service Delivery | Social welfare and community development | Support PWDs with funds and logistics to expand their business and pay their medical bills |  |  |  |  |  | 30,000 |  |  |  |  |  | Dept. of Soc. Dev’t | AyDA, Assembly members, PWDs Association, DHA, ISD |
| Development Dimension: Environment, Infrastructure and Human Settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Programmes | Sub-Programmes | Projects /Activities (Operations) | Location | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Programme status |  | Implementing Agencies |  |
|  |  |  |  |  | 1ST | 2ND | 3RD | 4TH | GOG |  | IGF | Donor | New | Ongoing | Lead | Collaborating |
|  |  |  |  |  |  |  |  |  | DACF | DDF |  |  |  |  |  |  |
| 47 | Infrastructure Delivery and management | Infrastructure development | Reshape 20km feeder roads and construct 5No. culverts in the District | District wide |  |  |  |  | 59,082 |  |  |  |  |  | DWD | AyDA, DFR, Assembly and unit C’ttee members, Contractors |
| 48 | Infrastructure Delivery and management | Physical and Spatial planning | Conduct regular inspection/ site selection to ensure development control | District wide |  |  |  |  |  |  | 5,000 |  |  |  | Physical Planning Dept | Developers, Land owners, SPC members |
| 49 | Infrastructure Delivery and management | Physical and Spatial planning | Organize monthly meetings of the SPC and the Technical Team | Coaltar |  |  |  |  |  |  | 5,000 |  |  |  | Physical Planning Dept | SPC members |
| 50 | Infrastructure Delivery and management | Physical and Spatial planning | Prepare sector layout for 3No. settlements | Coaltar, Teacher Mante and Dokro-chiwa |  |  |  |  |  | 20,000 |  |  |  |  | Physical Planning Dept | AyDA, Chiefs, Land owners, Assembly and Unit C’ttee members |
| 51 | Management and Administration | Finance and Revenue Mobilization | Carry out street Naming and Property Addressing exercise in the District | District wide |  |  |  |  | 50,000 |  |  |  |  |  | Physical Planning Dept | AyDA, Opinion Leaders, Landlords, Assembly & Unit C’ttee |
| 52 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |