AYENSUANO DISTRICT ASSEMBLY

2020 COMPOSITE ANNUAL ACTION PLAN

#### AYENSUANO DISTRICT ASSEMBLY

#### 2020 COMPOSITE ANNUAL ACTION PLAN

|  | Development Dimension: Governance, Corruption and Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | Programmes | Sub-Programmes | Projects /Activities (Operations) | Location | Outcome /Impact Indicators | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Implementing Agencies |  |
|  |  |  |  |  |  | 1ST | 2ND | 3RD | 4TH | GoG |  | IGF | Donor | Lead | Collaborating |
|  |  |  |  |  |  |  |  |  |  | DACF | DPAT |  |  |  |  |
| 1 | Management and Administration | Planning, Budgeting and Coordination | Organize quarterly public forum on the implementation of 2020 AAP and Budget | Coaltar | Increased local participation in Governance |  |  |  |  | 10,000 |  |  |  | Central Administraion | DPCU members, Stakeholders, Assembly members |
| 2 | Management and Administration | Planning, Budgeting and Coordination | Organize mid and annual performance review meetings on the implementation of 2020 AAP and Composite Budget | Coaltar | Increased understanding of Assembly concept and Increased Participation in governance |  |  |  |  | 15,000 |  |  |  | Central Administraion | DPCU members, Stakeholders, Assembly members, NGOs, ERCC |
| 3 | Management and Administration | Human Resource Management | Support staff on capacity building programme | Coaltar, Accra | Increased knowledge in Public Administration |  |  |  |  | 20,000 |  |  |  | Central Administraion | AyDA, Staff, Training Institutions, Consultants |
| 4 | Management and Administration | Planning, Budgeting and Coordination | Carry out monitoring on Development projects and Programmes with stakeholders | District wide | Increased participation in Local governance and quality work output |  |  |  |  | 20,000 |  |  |  | Central Administraion | DPCU members, Stakeholders, A/Ms Contractors, Area Council Executives |
| 5 | Management and Administration | General Administration | Organize quarterly meetings of the Assembly | Coaltar | Adherence to local governance protocol |  |  |  |  | 25,000 |  |  |  | Central Administraion | DPCU members, Sub-C’ttee and Executive C’ttee Members |
| 6 | Management and Administration | Planning, Budgeting and Coordination | Prepare 2021AAP,PP,Audit plan and Composite Budget | Coaltar | Increased participation in local governance |  |  |  |  | 20,000 |  |  |  | Central Administraion | DPCU members, Stakeholders, Assembly members |
| 7 | Management and Administration | General Administration | Organize and Support National Celebrations in the District (i.e. Independence day, May Day, etc) | District wide | Adherence to Government Policies |  |  |  |  | 30,000 |  |  |  | Central Administraion | Assembly members, community members |
| 8 | Management and Administration | General Administration | Provide Logistics and financial support to the Departments of the Assembly in the district | Coaltar | Efficiency in work output |  |  |  |  | 15,000 |  |  |  | Central Administraion | HoDs, PO, DFO |
| 9 | Management and Administration | Finance and Revenue Mobilization | Carryout maintenance on 4No. official Vehicles | Accra/ Koforidua | Efficient Vehicles |  |  |  |  | 20,000 |  |  |  | Central Administraion | AyDA, T/O Drivers, Mechanics |
| 10 | Management and Administration | General Administration | Purchase of office supplies and equipment (laptops,intenetboosters etc) | Accra/ Koforidua | Efficiency in work output |  |  |  |  | 12,000 |  |  |  | Central Administraion | AyDA, P/O, Tender C’ttee, Suppliers |
| 11 | Management and Administration | Human resource management | Training of management staff on local government protocols | Coaltar | Efficiency in work output |  |  |  |  |  |  | 44,500 |  | HR | Central Adm,Fin dept |
| 12 | Management and Administration | Human resource management | Training of revenue collectors on revenue mobilization | Coaltar | Enhanced revenue mobilization |  |  |  |  | 20,000 |  |  |  | HR | Central Adm,Fin dept |
| 13 | Management and Administration | General Administration | Support and strengthen sub structures | District wide | 3 number sub structures supported |  |  |  |  |  |  | 12000 |  | Area council | Central Administraion |
| 14 | Management and Administration | Security, law and order | Maintenance of security law and order | District wide | Improved security in the district |  |  |  |  |  |  | 6000 |  | DISEC | Central Administraion |
| 15 | Management and Administration | General Administration | Support MPs projects | District wide | Number of MPs projects supported |  |  |  |  | 45000 |  |  |  | MP | Central Administraion |

|  | Development Dimension: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | Programmes |  | Sub-Programmes |  |  | Projects /Activities (Operations) |  | Location |  |  | Outcome /Impact Indicators |  | Quarterly Time Schedule |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 1ST |  | 2ND |  | 3RD |  | 4TH |  | GoG |  |  |  | IGF |  | Donor |  | Lead |  | Collaborating |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DACF |  | DPAT |  |  |  |  |  |  |  |  |  |
| 16 | Management and Administration |  | Finance and revenue mobilization |  |  | Carry out data collection exercise and update of the District’s revenue database |  | District wide |  |  | Increase in internally generated fund |  |  |  |  |  |  |  |  |  | 20, 000 |  |  |  |  |  |  |  | Finance Dept. |  | AyDA, Revenue collectors, Assembly and unit committee members |  |
| 17 | Management and Administration |  | Finance and revenue mobilization |  |  | Preparation of revenue improvement action plan |  | Coaltar |  |  | Improved revenue mobilization |  |  |  |  |  |  |  |  |  | 8,000.00 |  |  |  | 15,000.00 |  |  |  | Finance Dept. |  | AyDA, Revenue collectors, Assembly and unit committee members |  |
| 18 | Management and Administration |  | Finance and revenue mobilization |  |  | Conduct routine pre-audit on all payment vouchers |  | District Wide |  |  | Number or payments pre-audited |  |  |  |  |  |  |  |  |  | 2,000 |  |  |  |  |  |  |  | Finance Dept. |  | AyDA, Revenue collectors, Assembly and unit committee members |  |
| 19 | Management and Administration |  | Finance and revenue mobilization |  |  | Conduct monthly evaluation on trial balance |  | District Wide |  |  | No. of evaluation organized |  |  |  |  |  |  |  |  |  | 4,000 |  |  |  |  |  |  |  | Finance Dept. |  | AyDA, Revenue collectors, Assembly and unit committee members |  |
| 20 | Economic Development |  | Trade, tourism and industrial development |  |  | Train 2 women groups in palm oil processing |  | District Wide |  |  | No. of women groups trained |  |  |  |  |  |  |  |  |  | 2,000.00 |  |  |  |  |  |  |  | NBSSI |  | Central Adm. |  |
| 21 | Economic Development |  | Trade, tourism and industrial development |  |  | Established a Business advisory centre |  | Coaltar |  |  | BAC established |  |  |  |  |  |  |  |  |  | 500000 |  |  |  |  |  |  |  | NBSSI |  | Central Adm. |  |
| 22 | Economic Development |  | Trade, tourism and industrial development |  |  | Training of Five 5 women in soap and powder making. |  | Selected communities |  |  | No. of training organized |  |  |  |  |  |  |  |  |  | 10,100.00 |  |  |  |  |  |  |  | NBSSI |  | Department of social Dev’t |  |
| 23 | Economic Development |  | Trade, tourism and industrial development |  |  | Train Women’s Groups and Unemployed Youth in Soap Making, auto mechanics, welding and Tailoring |  | Coaltar |  |  | Women’s Groups and Unemployed Youth trained in Soap Making |  |  |  |  |  |  |  |  |  | 7,000.00 |  |  |  |  |  |  |  | NBSSI |  | Department of social Dev’t |  |
| 24 | Economic Development |  | Trade, tourism and industrial development |  |  | Train women’s group in pomade, powder making and gari processing |  | Coaltar |  |  | Women’s group trained in pomade and powder making |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  | NBSSI |  | Department of social Dev’t |  |
| 25 | Economic Development |  | Agriculture Development |  |  | Organise RELC planning sessions for stakeholders |  | Coaltar, |  |  | Solutions to Agriculture challenges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,000 |  | Agric Dept. |  | AyDA, MoFA, Farmers, NGOs, FBOs, Researchers |  |
| 26 | Economic Development |  | Agriculture Development |  |  | Provide Direct extension services to farmers and FBOs by AEAS |  | District wide |  |  | Increase in yields and adherence to GAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3,000 |  | Agric Dept. |  | AyDA, MoFA, Farmers, NGOs, FBOs, Extension Officers |  |
| 27 | Economic Development |  | Agriculture Development |  |  | Facilitate for the establishment of one factory in the District |  | District Wide |  |  | District Factory established |  |  |  |  |  |  |  |  |  | 250,000.00 |  |  |  |  |  |  |  | IPEP, |  | Central Adm. |  |
| 28 | Economic Development |  | Agriculture Development |  |  | Mainstream gender into agriculture and food programmes |  | Coaltar |  |  | Number of agricultural programmes with gender issues |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  | Agric Dept. |  | CSOs |  |
| 29 | Economic Development |  | Agriculture Development |  |  | Identify and develop district tourist potentials |  | District Wide |  |  | Number of Tourism Potentials identify and developed |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  | Central Adm. |  | DPCU |  |
| 30 | Economic Development |  | Agriculture Development |  |  | Nursing2,000 Oil palm seedlings in selected communities |  | District Wide |  |  | No of Seedlings nursed |  |  |  |  |  |  |  |  |  | 300,000.00 |  |  |  |  |  |  |  | Dept. of Agric |  | Central Adm |  |
| 31 | Economic Development |  | Agriculture Development |  |  | Educate Farmers on the proper usage of agro-chemicals |  | District wide |  |  | No. of farmers educated |  |  |  |  |  |  |  |  |  |  |  |  |  | 7,000.00 |  |  |  | Dept. of Agric |  | Central Adm. |  |
| 32 | Economic Development |  | Agriculture Development |  |  | Train women on balance diet and education on food preservation |  | District wide |  |  | No. of women trained on balance diet and food preservation |  |  |  |  |  |  |  |  |  |  |  |  |  | 3,000.00 |  |  |  | Dept. of Agric |  | Central Adm. |  |
| 33 | Economic Development |  | Agriculture Development |  |  | Construct two tonner improved narrow ventilated maize crib for adoption by 100 farmers |  | Asuboi, Coaltar |  |  | Proper storage facility for Farmers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000 |  | Agric Dept |  | AyDA, MoFA, Farmers, NGOs, FBOs |  |
| 34 | Economic Development |  | Agriculture Development |  |  | Form sustainable value chain farmer groups to access local and international Markets |  | District wide |  |  | Increase in income levels |  |  |  |  |  |  |  |  |  |  |  |  |  | 1, 500 |  |  |  | Agric Dept. |  | AyDA, MoFA, Farmers, NGOs, FBOs |  |
| 35 | Economic Development |  | Agriculture Development |  |  | Organize farmers day celebration in the district |  | Coaltar |  |  | Farmers day celebrated |  |  |  |  |  |  |  |  |  | 40, 000 |  |  |  |  |  |  |  | Agric Dept. |  | AyDA, Chiefs, A/Ms,NGOs, Farmers, General Public |  |
|  | Development Dimension: Social Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/N | Programmes |  |  | Sub-Programmes |  |  | Projects /Activities (Operations) |  | Location | Outcome /Impact Indicators |  | Quarterly Time Schedule |  |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | 1ST |  |  | 2ND |  | 3RD |  | 4TH |  | GoG |  |  |  |  | IGF |  | Donor |  | Lead |  | Collaborating |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DACF |  | DPAT |  |  |  |  |  |  |  |  |  |
| 36 | Social Service Delivery |  |  | Education and Youth Development |  |  | Prepare ADEOP reports yearly |  | Coaltar | Number of ADEOP reports prepared |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,720 |  |  |  | GES |  | Central Adm. |
| 37 | Social Service Delivery |  |  | Education and Youth Development |  |  | Covid 19 training for office, heads and teachers |  | District-wide | Number of teachers trained |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5000 |  |  |  | GES |  | Central Adm. |
| 38 | Social Service Delivery |  |  | Education and Youth Development |  |  | Back to school campaign for office staff, head teachers and teachers |  | District-wide | Number of teachers trained |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5000 |  |  |  | GES |  | Central Adm. |
| 39 | Social Service Delivery |  |  | Education and Youth Development |  |  | Support needy but brilliant students in the District |  | District wide | Improved literacy |  |  |  |  |  |  |  |  |  |  | 20000 |  |  |  |  |  |  |  |  | GES |  | Central Adm. |
| 40 | Social Service Delivery |  |  | Education and Youth Development |  |  | Support STME Clinic and DEOC activities in the District |  | District wide | Improved Knowledge in Maths ,Science and Technology |  |  |  |  |  |  |  |  |  |  | 5000 |  |  |  |  |  |  |  |  | GES |  | Central Adm. |
| 41 | Social Service Delivery |  |  | Education and Youth Development |  |  | Support my first day at school |  | District-wide | Number of schools visited |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3000 |  |  |  | GES |  | Central Adm. |
| 42 | Social Service Delivery |  |  | Health Delivery |  |  | Support HIV/AIDS activities in the District |  | District wide | Reduction in prevalent rate |  |  |  |  |  |  |  |  |  |  | 18,542 |  |  |  |  |  |  |  |  | GHS |  | GAC, FP, NGOs, Health workers, Gen. public, |
| 43 | Social Service Delivery |  |  | Health Delivery |  |  | Support DHA on malaria programs in the District |  | District wide | Reduction in Malaria reported cases and increase in productivity |  |  |  |  |  |  |  |  |  |  | 15,000 |  |  |  |  |  |  |  |  | GHS |  | GHS, Gen. public, Health workers |
| 44 | Social Service Delivery |  |  | Health Delivery |  |  | Support COVID 19 immunization programmes |  | District wide | No. of people immunized |  |  |  |  |  |  |  |  |  |  |  |  | 6,000.00 |  |  |  |  |  |  | GHS |  | Central Adm |
| 45 | Social Service Delivery |  |  | Health Delivery |  |  | Sensitization campaign in communities, schools and churches/mosques on covid 19 protocols |  | District-wide | Number of campaigns organized |  |  |  |  |  |  |  |  |  |  |  |  | 3,000.00 |  |  |  |  |  |  | GHS |  | GES, FBOs, Public |
| 46 | Social Service Delivery |  |  | Health Delivery |  |  | Continue the distribution of Long Lasting Insecticide treated nets for pregnant women and children |  | District-wide | Number of ITNs supplied |  |  |  |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  | GHS |  | Households Donors |
| 47 | Social Service Delivery |  |  | Health Delivery |  |  | Organize District Response Management Team meetings on COVID 19 |  | Coaltar | Number of meetings held |  |  |  |  |  |  |  |  |  |  |  |  | 1,400.00 |  |  |  |  |  |  | GHS |  | MRMT, |
| 48 | Social Service Delivery |  |  | Health Delivery |  |  | Organize District AIDS Committee Meetings |  | District-wide | Number of meetings held |  |  |  |  |  |  |  |  |  |  |  |  | 1,800.00 |  |  |  |  |  |  | GHS |  | GAC |
| 49 | Social Service Delivery |  |  | Health Delivery |  |  | Conduct Voluntary Counseling and Testing at health facilities on COVID 19 |  | District-wide | Number of persons tested and results |  |  |  |  |  |  |  |  |  |  |  |  | 2,700.00 |  |  |  |  |  |  | GHS |  | GAC GHS |
| 50 | Social Service Delivery |  |  | Health Delivery |  |  | Organize District Health Committee Meetings on COVID 19 |  | Coaltar | Number of members present |  |  |  |  |  |  |  |  |  |  |  |  | 1,800.00 |  |  |  |  |  |  | GHS |  | Sub-district staff DHMT staff Selected HODs |
| 51 | Environmental and sanitation Management |  |  | Natural Resource Conservation |  |  | Sensitize communities and households on the need to construct domestic toilets |  | District-wide | Number of communities sensitized on domestic toilets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2000 |  |  |  | EHU |  | Landlords Assoc. DWST, |
| 52 | Environmental and sanitation Management |  |  | Natural Resource Conservation |  |  | Screen Food Vendors |  | District-wide | Food Vendors screened |  |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  |  | EHU |  | Central Adm. |
| 53 | Environmental and sanitation Management |  |  | Natural Resource Conservation |  |  | Educate communities against open defecation |  | Rural communities | Number of household toilets constructed under CLTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5000 |  |  |  | EHU |  | CLTS Land lords |
| 54 | Environmental and sanitation Management |  |  | Natural Resource Conservation |  |  | Procure and allocate personal protective equipment (PPEs) for Staff (EHOs, EHAs, labourers etc) |  | Accra/Coaltar | Quantities of protective gears procured and distributed |  |  |  |  |  |  |  |  |  |  | 4,000.00 |  |  |  |  |  |  |  |  | EHU |  | Central Adm. |
| 55 | Environmental and sanitation Management |  |  | Natural Resource Conservation |  |  | Place/locate litter bins at vantage areas |  | Lorry Parks Markets | Number of litter bins located |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2000 |  |  |  | EHU |  | Zoomlion Ghana Limited |
| 56 | Environmental and sanitation Management |  |  | Natural Resource Conservation |  |  | Carry out regular evacuation of communal containers |  | District-wide | Frequency of evacuation per week |  |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  |  | EHU |  | Zoomlion Ghana Limited |
| 57 | Social Service Delivery |  |  | Social welfare and community development |  |  | Organize study group meetings with women groups and VSLAs |  | District wide | Increase in income level |  |  |  |  |  |  |  |  |  |  | 3000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 58 | Social Service Delivery |  |  | Social welfare and community development |  |  | Sensitize women groups and girls on targeted programmes and services of the department |  | District wide | No of women trained |  |  |  |  |  |  |  |  |  |  | 6000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 59 | Social Service Delivery |  |  | Social welfare and community development |  |  | Conduct gender dialogues to raise awareness on the rights of women in the district |  | District wide | Improved knowledge of women |  |  |  |  |  |  |  |  |  |  | 5000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 60 | Social Service Delivery |  |  | Social welfare and community development |  |  | Support LEAP Programme in the District |  | LEAP communities | LEAP activities supported |  |  |  |  |  |  |  |  |  |  | 10000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 61 | Social Service Delivery |  |  | Social welfare and community development |  |  | Update PWDs register |  | District wide | PWDs register updated |  |  |  |  |  |  |  |  |  |  | 2000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 62 | Social Service Delivery |  |  | Social welfare and community development |  |  | Support PWDs with funds and logistics |  | District wide | PWDs supported |  |  |  |  |  |  |  |  |  |  | 3000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 63 | Social Service Delivery |  |  | Social welfare and community development |  |  | Register PWDs under Free NHIS |  | District wide | No of PWDs registered under NHIS |  |  |  |  |  |  |  |  |  |  | 5000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 64 | Social Service Delivery |  |  | Social welfare and community development |  |  | Train PWDs in additional livelihood skills/income generating activities (IGAs) |  | District wide | Increased level of incomes |  |  |  |  |  |  |  |  |  |  | 7000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 65 | Social Service Delivery |  |  | Social welfare and community development |  |  | Monitor activities of children in foster and care homes |  | District wide | No of foster homes monitored |  |  |  |  |  |  |  |  |  |  | 5000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 66 | Social Service Delivery |  |  | Social welfare and community development |  |  | Address child protection and family welfare cases in the district |  | District wide | No of child cases addressed |  |  |  |  |  |  |  |  |  |  | 4000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
| 67 | Social Service Delivery |  |  | Social welfare and community development |  |  | Carry out Day Care Monitoring in the District |  | District wide | Daycare centres monitored |  |  |  |  |  |  |  |  |  |  | 5000.00 |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  | AyDA, NGOs, women groups, ISD, NCCE |
|  | Development Dimension: Environment, Infrastructure and Human Settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/N | Programmes | Sub-Programmes |  |  | Projects /Activities (Operations) |  |  |  | Location | Outcome /Impact Indicators |  | Quarterly Time Schedule |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | 1ST |  | 2ND |  | 3RD |  | 4TH |  | GoG |  |  |  | IGF |  |  | Donor |  | Lead |  | Collaborating |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DACF |  | DPAT |  |  |  |  |  |  |  |  |  |  |
| 68 | Environmental Protection and Management | Natural Resource Conservation |  |  | Provide relief items to disaster victims |  |  |  | District Wide | No. victims provided with relief tems |  |  |  |  |  |  |  |  |  |  |  |  |  | 15,000.00 |  |  |  |  | NADMO |  | Central Adm. |  |
| 69 | Environmental Protection and Management | Natural Resource Conservation |  |  | Collaborate with Forestry Commission Plant trees to serve as windbreak in selected communities |  |  |  | District wide | No. of trees planted |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  | NADMO |  | Central Adm. |  |
| 70 | Environmental Protection and Management | Natural Resource Conservation |  |  | Re-afforestation of 10 hectares of degraded forest |  |  |  | District wide | Hectare of degraded forest recovered |  |  |  |  |  |  |  |  |  |  |  |  |  | 15,000.00 |  |  |  |  | FC |  | Central Adm. |  |
| 71 | Environmental Protection and Management | Natural Resource Conservation |  |  | Engagement of Forest fringe communities to plant food crops alongside tree seedlings to augment their income and boost reforestation. |  |  |  | Selected communities | No. of communities engaged |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  | FC |  | Central Adm. |  |
| 72 | Environmental Protection and Management | Natural Resource Conservation |  |  | Education/ Sensitization of fringe communities on forest conservation |  |  |  | District wide | No. of communities educated |  |  |  |  |  |  |  |  |  |  |  |  |  | 8,000.00 |  |  |  |  | FC |  | Central Adm. |  |
| 73 | Environmental Protection and Management | Natural Resource Conservation |  |  | Celebration of annual world tree planting day |  |  |  | District wide | World tree planting day observed |  |  |  |  |  |  |  |  |  |  |  |  |  | 6,000.00 |  |  |  |  | FC |  | Central Adm. |  |
| 74 | Infrastructure Delivery and management | Infrastructure development |  |  | Construct 3No. 3- units classroom blocks |  |  |  | Kraboa, Pampaso, Otoase | 3Number of classrooms constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 320,000.00 |  |  |  |  | DWD |  | Central Adm,GES |  |
| 75 | Infrastructure Delivery and management | Infrastructure development |  |  | Construct 4No. 6- units classroom blocks |  |  |  | Apeatu,Kofi pare,Aboabo presby | 4Number of classroom constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 540,000.00 |  |  |  |  | DWD |  | Central Adm,GES |  |
| 76 | Infrastructure Delivery and management | Infrastructure development |  |  | Construct 5No. CHPs compound with mechanized borehole and 2 Single rooms for health attendants |  |  |  | Besease, Sowatey, Krabokese, Mfranor,Bepoase | 5 Number of CHPs constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 25,000.00 |  |  |  |  | DWD |  | Central Adm,GHS |  |
| 77 | Infrastructure Delivery and management | Infrastructure development |  |  | Reshape 124km feeder roads and construct 5No. culverts in the District |  |  |  | District wide | Safe and accessible roads |  |  |  |  |  |  |  |  |  |  |  |  |  | 700,000 |  |  |  |  | DWD |  | Central Adm,DFR |  |
| 78 | Infrastructure Delivery and management | Infrastructure development |  |  | Construction of 1 no. 5 unit bungalow for DCE and DCD |  |  |  | Coaltar | No. of bungalows constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 420,000.00 |  |  |  |  | DWD |  | Central Adm. |  |
| 79 | Infrastructure Delivery and management | Infrastructure development |  |  | Drilling and Construction of 3No. Boreholes |  |  |  | AyibontAkukromAziaka,Kwame Takyi | 3No. boreholes constructed |  |  |  |  |  |  |  |  |  |  |  |  |  | 350,000.00 |  |  |  |  | DWD |  | Central Adm. |  |
| 80 | Infrastructure Delivery and management | Infrastructure development |  |  | Maintenance of infrastructure in the district |  |  |  | District wide | Improved infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  | DWD |  | Central Adm. |  |
| 81 | Infrastructure Delivery and management | Infrastructure development |  |  | Completion of 5no.CHPs with a borehole and 2unit single room |  |  |  | Govinakrom,Bepoase,Ayekokooso,Kraboakese and Obouho | 5Number of CHPs constructed |  |  |  |  |  |  |  |  |  | 400000 |  |  |  |  |  |  |  |  | DWD |  | Central Adm. |  |
| 82 | Infrastructure Delivery and management | Infrastructure development |  |  | Completion of 4no.2unit classrooms Blocks |  |  |  | Kuano,Kokosiase,Anumapam andKwadwo fosu | 4Number of classrooms constructed |  |  |  |  |  |  |  |  |  | 500000 |  |  |  |  |  |  |  |  | DWD |  | Central Adm. |  |
| 83 | Infrastructure Delivery and management | Physical and Spatial planning |  |  | Hold regular meeting of the Spatial Planning Committee |  |  |  | Coaltar | Number of meetings held |  |  |  |  |  |  |  |  |  | 5,000 |  |  |  |  |  |  |  |  | PPD |  | Developers Central Admin. |  |
| 84 | Infrastructure Delivery and management | Physical and Spatial planning |  |  | Organize Routine Building Inspection |  |  |  | District wide | No. of inspection organised monthly |  |  |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  | PPD |  | DWD |  |