AYENSUANO DISTRICT ASSEMBLY

2021 COMPOSITE ANNUAL ACTION PLAN

#### COMPOSITE ANNUAL ACTION PLAN OF AYENSUANO DISTRICT ASSEMBLY FOR 2021

|  | Development Dimension: Governance, Corruption and Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | Programmes | Sub-Programmes | Projects /Activities (Operations) | Location | Outcome /Impact Indicators | Quarterly Time Schedule |  |  |  | Indicative Budget |  |  |  | Implementing Agencies |  |
|  |  |  |  |  |  | 1ST | 2ND | 3RD | 4TH | GoG |  | IGF | Do-nor | Lead | Collaborating |
|  |  |  |  |  |  |  |  |  |  | DACF | DDF |  |  |  |  |
| 1 | Management and Administration | Planning, Budgeting and Coordination | Organize quarterly public forum on the implementation of 2021 AAP and Budget | Coaltar | Increased local participation in Governance |  |  |  |  | 10,000 |  |  |  | Central Adm. | DPCU members, Stakeholders, Assembly members |
| 2 | Management and Administration | Planning, Budgeting and Coordination | Organize mid and annual performance review meetings on the implementation of 2021 AAP and Composite Budget | Coaltar | Increased understanding of Assembly concept and Increased Participation in governance |  |  |  |  | 15,000 |  |  |  | Central Adm. | DPCU members, Stakeholders, Assembly members, NGOs, ERCC |
| 3 | Management and Administration | Human Resource Management | Support staff on capacity building programme | Coaltar, Accra | Increased knowledge in Public Administration |  |  |  |  | 20,000 |  |  |  | Central Adm. | AyDA, Staff, Training Institutions, Consultants |
| 4 | Management and Administration | Planning, Budgeting and Coordination | Carry out monitoring on Development projects and Programmes with stakeholders | District wide | Increased participation in Local governance and quality work output |  |  |  |  | 20,000 |  |  |  | Central Adm. | DPCU members, Stakeholders, A/Ms Contractors, Area Council Executives |
| 5 | Management and Administration | General Administration | Organize quarterly meetings of the Assembly | Coaltar | Adherence to local governance protocol |  |  |  |  | 25,000 |  |  |  | Central Adm. | DPCU members, Sub-C’ttee and Executive C’ttee Members |
| 6 | Management and Administration | General Administration |  | Coaltar | Increased participation in local governance |  |  |  |  | 24,000 |  |  |  | Central Adm. | Increased participation in local governance |
| 7 | Management and Administration | Planning, Budgeting and Coordination | Prepare 2022 District Composite Budget | Coaltar | Increased participation in local governance |  |  |  |  | 20,000 |  |  |  | Central Adm. | Increased participation in local governance |
| 8 | Management and Administration | General Administration | Organize and Support National Celebrations in the District (i.e. Independence day, May Day, etc) | District wide | Adherence to Government Policies |  |  |  |  | 30,000 |  |  |  | Central Adm. | Assembly members, community members |
| 9 | Management and Administration | General Administration | Provide Logistics and financial support to the Departments of the Assembly in the district | Coaltar | Efficiency in work output |  |  |  |  | 15,000 |  |  |  | Central Adm | HoDs, PO, DFO |
| 10 | Management and Administration | General Administration | Procure 1No. Motor bike for the Assembly | Accra/ Koforidua | Efficiency in work output |  |  |  |  | 5,000 |  |  |  | Central Adm | PO, TO, Tender C’ttee, Suppliers |
| 11 | Management and Administration | Finance and Revenue Mobilization | Carryout maintenance on 4No. official Vehicles | Accra/ Koforidua | Efficient Vehicles |  |  |  |  | 20,000 |  |  |  | Central Adm | AyDA, T/O Drivers, Mechanics |
| 12 | Management and Administration | General Administration | Procure 3No. Laptops and 2No. Desktops for official use | Accra/ Koforidua | Efficiency in work output |  |  |  |  | 12,000 |  |  |  | Central Administraion | AyDA, P/O, Tender C’ttee, Suppliers |
| 13 | Infrastructure delivery and Management | Infrastructure Development | Carry out extension of streetlights and replacement of street light bulbs in the District | District wide | Enhanced public safety |  |  |  |  | 20,000 |  |  |  | Phyical Planning Dept. | Assembly and unit C’ttee members, Trad. Auth., MP, NGOs, Com. members. |

|  | Development Dimension: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | Programmes | Sub-Programmes |  |  | Projects /Activities (Operations) |  |  | Location |  | Outcome /Impact Indicators |  |  | Quarterly Time Schedule |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 1ST |  | 2ND |  | 3RD |  | 4TH |  | GoG |  |  |  | IGF |  |  | Donor |  |  | Lead |  |  | Collaborating |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DACF | DDF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Management and Administration | Finance and revenue mobilization |  |  | Carry out data collection exercise and update of the District’s revenue database |  |  | District wide |  | Increase in internally generated fund |  |  |  |  |  |  |  |  |  |  | 20, 000 |  |  |  |  |  |  |  |  |  | Finance Dept. |  |  | AyDA, Revenue collectors, Assembly and unit committee members |  |  |  |  |
| 15 | Economic Development | Agriculture Development |  |  | Establish Demonstration farms at the three Area Councils |  |  | Coaltar, Anum Apapam, Asuboi |  | Improved seeds/ planting materials for farmers and knowledge in GAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3,000 |  |  | Agric Dept |  |  | AyDA, MoFA, Farmers, NGOs, FBOs |  |  |  |  |
| 16 | Economic Development | Agriculture Development |  |  | Organise RELC planning sessions for stakeholders |  |  | Coaltar, |  | Solutions to Agriculture challenges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5,000 |  |  | Agric Dept. |  |  | AyDA, MoFA, Farmers, NGOs, FBOs, Researchers |  |  |  |  |
| 17 | Economic Development | Agriculture Development |  |  | Support the PFJ programme in the District to achieve One District one exportable crop/ factory |  |  | District wide |  | Employment and Job Opportunities |  |  |  |  |  |  |  |  |  |  | 10, 000 |  |  |  |  |  |  |  |  |  | Agric Dept |  |  | AyDA, MoFA, Farmers, NGOs, FBOs, Extension Officers |  |  |  |  |
| 18 | Economic Development | Agriculture Development |  |  | Provide Direct extension services to farmers and FBOs by AEAS |  |  | District wide |  | Increase in yields and adherence to GAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3,000 |  |  | Agric Dept. |  |  | AyDA, MoFA, Farmers, NGOs, FBOs, Extension Officers |  |  |  |  |
| 19 | Economic Development | Agriculture Development |  |  | Form sustainable value chain farmer groups to access local and international Markets |  |  | District wide |  | Increase in income levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,500 |  |  |  |  |  | Agric Dept. |  |  | AyDA, MoFA, Farmers, NGOs, FBOs |  |  |  |  |
| 20 | Economic Development | Agriculture Development |  |  | Organize farmers day celebration in the district |  |  | Coaltar |  |  |  |  |  |  |  |  |  |  |  |  | 40, 000 |  |  |  |  |  |  |  |  |  | Agric Dept. |  |  | AyDA, Chiefs, A/Ms,NGOs, Farmers, General Public |  |  |  |  |
| 21 | Economic Development | Trade, tourism and industrial development |  |  | Support for LED Activities - Establish processing centres in the District |  |  | Amanase Aboabo, Kwaboanta |  | Enhanced production |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 200, 000 |  |  | Dept. of Social dev’t. |  |  | AyDA, Chiefs, Enterprise groups, NGO |  |  |  |  |
|  | Development Dimension: Social Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/N | Programmes |  |  | Sub-Programmes |  |  | Projects /Activities (Operations) |  | Location |  | Outcome /Impact Indicators | Quarterly Time Schedule |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | 1ST |  |  | 2ND |  | 3RD |  | 4TH | GoG |  |  |  |  |  |  | IGF |  |  | Donor |  |  | Lead |  |  | Collaborating |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DACF |  |  |  | DDF |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Construct 1No. 6-units classroom block |  | Nana Apeatu |  | Increase in enrollment and Conducive environment for teaching and learning |  |  |  |  |  |  |  |  |  |  |  |  | 35,000 |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, GET Fund, MLGRD,DDF, Community, GES |
| 23 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Rehabilitate 1No. 6-units classroom block |  | Amanase Homesu MTN |  | Increase in enrollment and Conducive environment for teaching and learning |  |  |  |  |  |  |  |  |  |  |  |  | 200,000 |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, GET Fund, MLGRD,DDF, Community, GES |
| 24 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Construct 1No. 3- units JHS classroom block |  | Nana Boame |  | Increase in enrollment and Conducive environment for teaching and learning |  |  |  |  |  |  |  |  |  |  |  |  | 300,000 |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, GET Fund, MLGRD,DDF, Community, GES |
| 25 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Rehabilitate 1No. 3- units classroom block |  |  |  | Increase in enrollment and Conducive environment for teaching and learning |  |  |  |  |  |  |  |  |  |  |  |  | 120,000 |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, GETFund, Contractor, consultant, Community, GES |
| 26 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Rehabilitate 1No. CHPs compound |  | Teacher Mante |  | Improved access to health delivery |  |  |  |  |  |  |  |  |  |  |  |  | 220,000 |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, Contractor, consultant, Community, DHD |
| 27 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Construct 2No. 2- units K.G block and ancillary facilities |  | Larteh Mante, Asiam Ningo |  | Increased in enrollment and Conducive environment for teaching and learning |  |  |  |  |  |  |  |  | 350,000 |  |  |  | 200,000 |  |  |  |  |  |  |  |  | DWD |  |  | GET Fund, MLGRD,DDF, Community, GES |
| 28 | Social Service Delivery |  |  | Education and Youth Development |  |  | Support needy but brilliant students in the District |  | District wide |  | Improved literacy level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 60, 000 |  |  |  |  |  | GES |  |  | A/Ms, Circuit Supervisors, Headteachers, SMCs |
| 29 | Social Service Delivery |  |  | Education and Youth Development |  |  | Support STMIE Clinic activities in the District |  | District wide |  | Improved Knowledge in Maths ,Science and Technology |  |  |  |  |  |  |  |  | 9,000 |  |  |  |  |  |  |  |  |  |  |  |  | GES |  |  | AyDA, PTAs/SMCs, pupils, Parents |
| 30 | Social Service Delivery |  |  | Education and Youth Development |  |  | Support and expand School Feeding Programme |  | District wide |  | Increase in enrollment |  |  |  |  |  |  |  |  | 10,000 |  |  |  |  |  |  |  |  |  |  |  |  | GES |  |  | AyDA, MGCSP, DHA, PTAs/SMCs, |
| 31 | Social Service Delivery |  |  | Health Delivery |  |  | Construct 1No. CHPs compound with mechanized borehole and 2 Single rooms for health attendants |  | Akotua krom |  | Easy Access to Health facilities. Improved health care delivery |  |  |  |  |  |  |  |  | 230,000 |  |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, Dist. Health Admin, Community members, Assembly & Unit committee members, Contractors |
| 32 | Social Service Delivery |  |  | Health Delivery |  |  | Register 1000 persons above 70 years under free NHIS |  | District wide |  | Easy, accessible and affordable healthcare |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  | Dept of Soc. Dev’t |  |  | AyDA, NCCE, NGOs, MP, Aged, CHRAJ, Chiefs |
| 33 | Social Service Delivery |  |  | Health Delivery |  |  | Support HIV/AIDS activities in the District |  | District wide |  | Reduction in prevalent rate |  |  |  |  |  |  |  |  | 12,000 |  |  |  |  |  |  |  |  |  |  |  |  | DHA |  |  | GAC, FP, NGOs, Health workers, Gen. public, |
| 34 | Social Service Delivery |  |  | Health Delivery |  |  | Support DHA on malaria programs in the District |  | District wide |  | Reduction in Malaria reported cases |  |  |  |  |  |  |  |  | 15,000 |  |  |  |  |  |  |  |  |  |  |  |  | DHA |  |  | GHS, Gen. public, Health workers |
| 35 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Drill and Construct 10No. boreholes in the District |  | Teacher Asiedu, Yaw Larbi |  | Improved access to safe drinking water |  |  |  |  |  |  |  |  | 250,000 |  |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, NGOs, Community members, Assembly &Unit C’ttee members, WATSANC, |
| 36 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Drill and construct 1No. mechanized borehole |  | Teacher Mante |  | Improved access to safe drinking water |  |  |  |  |  |  |  |  | 51,200 |  |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, NGOs, Community members, Assembly &Unit C’ttee members, WATSANC, |
| 37 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Rehabilitate 5No. boreholes in the District |  | Okoe Nkwanta, Kwaboanta Jn. etc |  | Improved access to safe drinking water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 75,000 |  |  |  |  |  | DWD |  |  | AyDA, NGOs, Community members, Assembly &Unit C’ttee members, WATSANC, Contractors |
| 38 | Environmental and sanitation Management |  |  | Natural Resource Conservation |  |  | Evacuate refuse dumps in the District |  | Some selected communities in the District |  | Reduction in the spread of air-borne diseases |  |  |  |  |  |  |  |  | 320, 000 |  |  |  |  |  |  |  |  |  |  |  |  | DEHU |  |  | AyDA, Zoomlion, Traditional Authorities |
| 39 | Infrastructure Delivery and Management |  |  | Infrastructure Development |  |  | Construct 12 Seater W/C toilet facility |  | Amanase |  | Prevention of open defecation and the spread of air-borne diseases |  |  |  |  |  |  |  |  | 230, 000 |  |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, DEHU, Chiefs, Contractors |
| 40 | Management and Administration |  |  | Human Resource Management |  |  | Support the Nations Builders Corps (NaBCO) programme |  | Coaltar |  | Increase in employment and job opportunities |  |  |  |  |  |  |  |  | 10,000 |  |  |  |  |  |  |  |  |  |  |  |  | Central Administraion |  |  | AyDA, |
| 41 | Social Service Delivery |  |  | Social welfare and community development |  |  | Train 10 women Groups in group dynamics, entrepreneurial skills, home management and records keeping |  | Coaltar |  | Increase in income level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000 |  |  | Dept. of Soc. Dev’t |  |  | AyDA, NBSSI, NGOs, Women groups , trainers |
| 42 | Social Service Delivery |  |  | Social welfare and community development |  |  | Train women groups in tye and dye and soap making |  | District wide |  | Increase in livelihood activities and level of income |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000 |  |  | Dept. of Soc. Dev’t |  |  | AyDA, NBSSI, NGOs, women groups , trainers |
| 43 | Social Service Delivery |  |  | Social welfare and community development |  |  | Support children in deprived communities with free school uniforms, bags, exercise books and foot wears |  | District wide |  | Increase in enrolment levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10,000 |  |  | Dept. of Soc. Dev’t |  |  | AyDA, MGCSP, Assembly members, teachers , pupils, Parents, NGOs |
| 44 | Social Service Delivery |  |  | Social welfare and community development |  |  | Support LEAP Programme in the District |  | District wide |  | Increase in household income level |  |  |  |  |  |  |  |  | 10,000 |  |  |  |  |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  |  | AyDA, MGCSP, Assembly members, Trad. Auth. Aged, CLIC mem. ISD |
| 45 | Social Service Delivery |  |  | Social welfare and community development |  |  | Support PWDs with funds and logistics to expand their business and pay their medical bills |  |  |  |  |  |  |  |  |  |  |  |  | 25,000 |  |  |  |  |  |  |  |  |  |  |  |  | Dept. of Soc. Dev’t |  |  | AyDA, Assembly members, PWDs Association, DHA, ISD |
|  | Development Dimension: Environment, Infrastructure and Human Settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/N | Programmes |  | Sub-Programmes |  |  | Projects /Activities (Operations) |  |  | Location |  | Outcome /Impact Indicators | Quarterly Time Schedule |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | 1ST |  | 2ND |  | 3RD |  | 4TH |  | GoG |  |  |  |  |  | IGF |  |  | Donor |  |  | Lead |  |  | Collaborating |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DACF |  |  | DDF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 46 | Infrastructure Delivery and management |  | Infrastructure development |  |  | Reshape 20km feeder roads and construct 5No. culverts in the District |  |  | District wide |  | Safe and accessible roads |  |  |  |  |  |  |  |  | 80,000 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | AyDA, DFR, Assembly and unit C’ttee members, Contractors |  |  |
| 47 | Infrastructure Delivery and management |  | Physical and Spatial planning |  |  | Conduct regular inspection/ site selection to ensure development control |  |  | District wide |  | Harmonized development of human settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7,000 |  |  |  |  |  | Physical Planning Dept |  |  | Developers, Land owners, SPC members |  |  |
| 48 | Infrastructure Delivery and management |  | Physical and Spatial planning |  |  | Organize monthly meetings of the SPC and the Technical Team |  |  | Coaltar |  | Effectiveness in spatial planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  | Physical Planning Dept |  |  | SPC members |  |  |
| 49 | Infrastructure Delivery and management |  | Physical and Spatial planning |  |  | Prepare sector layout for 3No. settlements |  |  |  |  | Harmonized development of human settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 30,000 |  |  |  |  |  | Physical Planning Dept |  |  | AyDA, Chiefs, Land owners, Assembly and Unit C’ttee members |  |  |
| 50 | Management and Administration |  | Finance and Revenue Mobilization |  |  | Carry out street Naming and Property Addressing exercise in the District |  |  | District wide |  | Increase in internally generated revenue |  |  |  |  |  |  |  |  | 60,000 |  |  |  |  |  |  |  |  |  |  |  | Physical Planning Dept |  |  | AyDA, Opinion Leaders, Landlords, Assembly & Unit C’ttee |  |  |