AYENSUANO DISTRICT ASSEMBLY

REVISED 2025 ANNUAL ACTION PLAN

| DEVELOPMENT DIMENSION : GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Program me(PBB) | Sub- programm e(PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCE GH(Ȼ) |  | INDICATORS (output/impact) | Programme Status |  | Implementing Institution/Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | new | On going | Lead | Collaborating |
| 1. | P4: MANAGEMENT AND ADMINISTRATION | SP4.1: General Administration | Celebration of National Events (Farmers day, May day) | District wide |  |  |  |  | 20,000.00 | DACF | Celebration of day |  | Ongoing | Central Admin | All Departments |
| 2. |  |  | Organize 3 Number statutory meeting for each of the 5 sub commites ( Development Planning, Works, Agric and Environmental, Social Services and Justice and Security) | District Office |  |  |  |  |  | DACF | Statutory meeting |  | Ongoing | Central Admin | All Departments All stakeholders |
| 3 |  |  | Organize Community Engagement At Obesua, Anuum Apapamu And Coaltar Area Councils | Obesua, Anuum Apapamu And Coaltar Area Councils |  |  |  |  | 3,000.00 | DACF | Statutory meeting |  | Ongoing | Procurem ent Dept. | Central Admin. Budget Unit |
| 4. |  |  | Organize 3 Number General Assembly Meetings | Obesua, Coaltar, Anum Apapamu |  |  |  |  | 5,000.00 | DACF | Meeting |  | ongoing | Admin | Central Admin |
| 5 |  |  | Organization of quarterly PRCC meetings | District Assembly |  |  |  |  | 5,000.00 | DACF | Statutory Meeting |  | ongoing | Central Admin | Central Admin |
| 6 |  |  | Organize quarterly Management meetings | District Assembly |  |  |  |  | 17,000.00 | DACF | Statutory meeting |  | Ongoing | Central admin | Management |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | organization of 2 no. Town Hall Meetings | Obesua And Coaltar Area |  |  |  |  | 16,000.00 | DACF | Statutory Meeting |  | ongoing | Admin | Central Admin |
| 8 |  |  | Conduct quarterly Monitoring And Evaluation Of Programmes And Projects. | Entire District |  |  |  |  | 10,000.00 | DACF | Quality assurance for results orientation |  | Ongoing | DPCU | Development Planning |
| 9. |  |  | Organise A Sensitization Exercise On Farm Safety And Hygiene For Obesua And Coaltar Area Councils | District wide |  |  |  |  | 1,000.00 | IGF | No. of people educated |  | Ongoing | NCCE | DEHU, NADMO |
| 10 |  |  | Organize 3 Number Executive Committee Meetings | District Office |  |  |  |  | 4,000.00 | IGF | Statutory meeting |  | Ongoing | Admin | Central Admin. |
| 11 |  |  | Preparation of 2026 Operations and Maintenance Plan | District wide |  |  |  |  | 4,000.00 | GOG | Plan preparation |  | Ongoing | DPCU | Central Admin |
| 12 |  |  | Organize an orientation/training for Assembly Members on Child Protection/ Child Labour issues in district and need to tackle it holistically | Anum Apapmu |  |  |  |  | 5,000.00 | IGF |  |   |  | SWCD | UNICEF |
| 13. |  |  | Organize Quarterly Monitoring And Evaluation | District Office |  |  |  |  | 45,000.00 | DACF | Improve Human resources |  |   | HR | Central Admin |
| 14. |  |  | Organize training/ capacity building workshop for SMC/PTA in selected communities across the district to champion advocacy against child labour at the local level and improve outcomes | Selected communities |  |  |  |  | 7,000.00 | DACF | To discourage child labour |  | Ongoing | SWCD | UNICEF |
| 15 |  |  | Embark on data collection exercise to update businesses and ratable property datsbase |  |  |  |  |  | 50,000 | DACF | For planning and development |  |  | DPCU | All Departments & Units |
| 16. |  |  | Training workshop on performance management | District assembly |  |  |  |  | 10,000.00 | DACF | Improve governance and accountability |  |   | DPCU | Community stakeholders |
| 17. | P4: MANAGEMENT AND ADMINISTRATION |  | Data Collection On Teenage Pregnancy; Causes And Implications For The Development Of The District | District Office |  |  |  |  | 30,000.00 | DACF | For budgeting and revenue collection |  |  | Budget Unit | DPCU |
| 18. |  | SP4.1: General Administration | Data Gathering On Hospitality Facilities In The District | District wide |  |  |  |  | 10,00 0 | DACF | For decision making and development |  |  | Statistics Dept. | All Departments & Units |
| 19. |  |  | Undertake Revenue Sensitization For Rate Payers | District wide |  |  |  |  | 3,00 0.00 | DACF | To track progress in the district |  |  | Statistics Dept. | DPCU |
| 20. |  |  | Monitor Revenue Collection Quarterly. | District wide |  |  |  |  | 4,000.00 | DACF | To help control teenage pregnacy |  |  | Statistics Dept. | Social Welfare and Community Development |
| 21. |  |  | Internal Security Operations | District wide |  |  |  |  | 10,000.00 | IGF | To improve citizen understanding of taxes |  |  | Finance Dept. | Budget |
| 22. |  |  | Monitoring And Evaluation Of Programmes And Projects Quarterly. | District wide |  |  |  |  | 2,000.00 | IGF | Accountability and information giving |  |  | Finance Dept. | MIS, Budget Depts. |
| 23. |  |  | GIFMIS Operations | District wide |  |  |  |  | 30,000.00 | DACF | Ensure efficient use of resources |  |  | DPCU | Stakeholders, Assembly members, community members. |
| 24. |  |  | Audit Committee & Work Plan | District Office |  |  |  |  | 20,000.00 | DACF | Increase participation in local governance |  |  | Central Admin. | Legislative committee members |
| 25. |  |  | Maintenance of vehicles | District wide |  |  |  |  | 5,000.00 | DACF | Increase participation in local governance |  |  | Central Admin. | Stakeholders |
| 26. |  |  | Organize bi annual Road safety training for Okada/motor riders in Coalfar | District Office |  |  |  |  | 40,000.00 | IGF | Human resource strengthening |  |  | Central Admin |  |
| 27. |  |  | Data Collection of water facilities within the district. | District Office |  |  |  |  | 50,000.00 | IGF | Increase value for money |  |  | Fin. Dept. | Revenue collectors, unit committee members |
| 28. |  |  | Revision of 2025 AAP | District Office |  |  |  |  | 30,000.00 | DACF | Increase productivity and accountability. |  |  | Internal Audit | Finance Dept., stakeholders |

| DEVELOPMENT DIMENSION:ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Program me (PBB) | Sub- programm e(PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCE(GHȻ) |  | INDICATORS (OUTPUT/IMPACT | Programme Status |  | Implementing Institution/Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | New | Ongoi ng | Lead | Collaborating |
| 29. | ECONOMIC DEVELOPMENT SDGs GOAL 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all P1:ECONO MIC DEVELOPM ENT | SP1.1: Trade, Industry and Tourism Services SP1.2:Agri culture Services and Management | Organize 4 No. Local Economic Development meetings | District Office |  |  |  |  | 6,000. 00 | DACF | Improve local economic development |  |  | DPCU | District Planning Coordinating Unit |
| 30 |  |  | Organization of 3 no. business fora | Sowatey, Alafia, Obouho, Oparekrom , Pepoase, Marfokrom |  |  |  |  | 3,000.00 | DACF | Meeting |  |  | Agric. Dept | Central Admin, Farmers |
| 31. |  |  | Organize 1 RELC Session for stakeholders | District Office |  |  |  |  | 7,550.00 | DACF Donor | Stakeholders in Agric engagement |  |  | Agric Dept. | Central Admin., Stakeholders |
| 32. |  |  | Train youth interested in TVET | District Office |  |  |  |  | 12,000. 00 | DACF | Increase job opportunities |  |  | DPCU | SWCD GEA |
| 33. |  |  | Organize meetings and field visits to local Industries | District wide |  |  |  |  | 3,000 | IGF | Enhance cooperation between industries and the assembly |  |  | DPCU | Central Admin. |
| 34. |  |  | Prepare Tourism profile for Obuoho water fall | Obuoho |  |  |  |  | 10,000 | DACF | Enhance tourism potential in Obuoho |  |  | DPCU | Central Admin |
| 35 |  |  | Organize 6no. farmer fora and sensitization on climate change by December 2025 | Govina, Abogzi. Mensahkrom, Okonkwanta, Ntowkrom, Ayekwesi |  |  |  |  | 7,000.00 | DACF | Appreciate the worth of farmers |  |  | Agric. Dept. | Central Admin. |
| 36 |  |  | Train 50 Youth in bead making | District wide |  |  |  |  | 23,000.00 | IGF | Youth empowerment |  |  | Agric. Depart. | MAG EXT |
| 37 |  |  | Reshaping of Asuboi- Apauwawase farm land road 4.0km | Asuboi- Apauwawase |  |  |  |  | 575,000 | IGF/ DACF | Create access to Apauwawase farm land |  |  | Agric. Dept. |  |
| 38 | SDG Target 8.3: Promote development oriented policies that support productive activities, decent job creation, entrepreneurship, creativity and innovation, and encourage the formalization and Growth of micro, small and medium sized enterprises, including through access to financial services |  | Train 20 vegetable farmers on safe-use of Agro- chemicals by October, 2025 | Kyekyewere |  |  |  |  | 1,000.00 | IGF | To track progress of crops and livestock |  |  | Agric. Dept. | MAG/MOFA |
| 39. |  |  | Participate in Eastern commodity fair by October,2025 | Koforidua |  |  |  |  | 40,800.00 | DACF | To support Agric. production in the district |  |  | Agric Dept. | MAG/MOFA |
| 40. |  |  | Train 2 women groups on preservation of leafy vegetable by June 2025 | Krabokese, Abodzi |  |  |  |  | 5,500 | DACF | Demonstration farms established |  |  | Agric. Dept. | MOFA |
| 41. |  |  | Train 40 women farmers for women FBOs on postharvest handling of grains by July 2025 | Asuboi, |  |  |  |  | 2,000.00 | DACF | Increase access to veterinary services |  |  | Agric. Dept. | MOFA |
| 42. |  |  | Procure 1 Number Gari Fryer and Compressor for Amanase Gari Cooperative | Amanase, Asuboi |  |  |  |  | 1,200.00 |  | Promote agroprocessing and value addition in the district |  |  | Agric. Dept. |  |
| 43 |  |  | Prepare National Disaster Preparedness Action Plan |  |  |  |  |  | 35,000 |  | Disaster Preparedness Plan Prepared |  |  | NADMO | DPCU |
|  |  |  | Organize green Ghana Day (Tree Planting exercise) | District wide |  |  |  |  | 40,000 |  | Green Ghana Day Organized |  |  |  |  |
| 44 |  |  | Embark on land reclamation of sand winning and gold mining sites | District wide |  |  |  |  | 930.00 | DACF | Land reclaimed |  |  | NADMO. | MOFA |
| 45. |  |  | Organization of quarterly LED meetings | 10 selected communities |  |  |  |  | 2,000.00 | DACF | Improve Economic Development |  |  | GEA | DPCU |
| 46 |  |  | Support LED through rapid needs assessment to inform building process through training and re-tooling where necessary of new and existing businesses to enhance job creation | District wide |  |  |  |  | 4,000.00 | DACF | Improve economic development |  |  | GEA | DPCU |

| DEVELOPMENT DIMENSION : SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Program me (PBB) | Sub- programm e(PBB) |  | Broad Activities | Location | Timeframe |  |  |  | FINANCE(GHȻ) |  |  |  | INDICATORS (OUTPUT/IMPACT) | Programme Status |  |  |  | Implementing Institution/Department |  |  |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST |  | SOURCE |  |  | New |  | Ong oing |  | Lead |  | Collaborating |
| 47. | P2: SOCIAL SERVICES DELIVERY | SP2.1: Environmental Health and Sanitation Services |  | Organise a refresher training for Staff & Stakeholders (CHRAJ, GHS, NCCE, GES, DOVVSU, NGO/CSOs, Traditional Leaders, FBOs etc) on use of CP Toolkits | District wide |  |  |  |  | 6,000.00 |  | GOG |  | 30 Stakeholders and staff trained on ISS for improved delivery of services |  |  |  |  | EHSU |  | Zoomlion, NADMO |
| 48. |  |  |  | Embark on home visits and case follow-ups to identify and deal will cases of school drop-outs, teenage mothers, child seclusion and refer for the appropriate social services | Selected communities |  |  |  |  | 4,000.00 |  | UNICEF |  | To promote child protection sensitization |  |  |  |  | DCPC |  | DBO/DPCU |
| 49. |  |  |  | Conduct Community Engagement using the Child Protection Toolkits in 50 communities tackling Child Labour, Parenting, Child Abuse, Adolescent & Mental Health, "Boys and Girls Roles", etc. | Selected communities |  |  |  |  | 9,500.00 |  | UNICEF |  | Community engagement in 40 communities conducted |  |  |  |  | DCPC |  | Identified CSOs / Private Enterprises |
| 50. |  |  |  | Follow-up on child protection/SGBV cases and strengthen Referral And Linkage Services for clients | Selected communities |  |  |  |  | 2,000.00 |  | UNICEF |  | Number of children increasingly benefiting from lntegrated Social Services (including Children Reunited From RHC To Family, Children Survivor Of SGBV, Children Withdrawn From Worst Forms Of Child Labour, Children Rescued Of Trafflcking, Etc |  |  |  |  | FP |  | Identified CSOs / Private Enterprises |
| 51. |  |  |  | Strengthen/ form new Community Child Protection Committees (CCPCs) in five communities | District wide |  |  |  |  | 6,000.00 |  | UNICEF |  | CCPCs formed in 5 communities |  |  |  |  | DCPC |  | UNICEF – CP |
| 52. |  |  |  | Train Adolescent mothers and other vulnerable women groups in livelihood and Entrepreneurial skills | District office |  |  |  |  | 4,500.00 |  | UNICEF |  | At least 20 day care centres monitored and supported to register |  |  |  |  | DCPC |  | UNICEF – SPI/ SWCD |
| 53. |  |  |  | Train adolescents and young people in skilling, job matching, employability and advocacy-related support | District office |  |  |  |  | 4,700.00 |  | UNICEF |  | World Day Against Child Labour marked to create public awareness on the need to end child labour |  |  |  |  | SWCD |  | UNICEF - SPI |
| 54. |  |  |  | Organization of bi annual Intersectoral Meeting | District Assembly |  |  |  |  | 10,000.00 |  | IGF |  | Statutory Meeting |  |  |  |  | DPCU |  | Central Admin |
| 55. |  |  |  | Collaborate with Police, CCPCs and key stakeholders to apprehend and profile children/ parents/caregivers identified engaging in child labour on market days, and manage cases | District office |  |  |  |  | 12,000.00 |  | UNICEF |  | At least 10 market swoops in large market centres organised to rescue children engaged in child labour |  |  |  |  | DPCU |  | UNICEF - SPI |
| 56. |  |  |  | Support PWDs with funds and logistics as well as appropriate rehabilitation | District office |  |  |  |  | 15,000.00 |  | UNICEF |  | At least 150 PWDs supported in various livelihood ventures |  |  |  |  | MELR-CLU |  | UNICEF – CP |
| 57. |  |  |  | Organize mass education on DSWCD services and programmes of the District Assembly | District office |  |  |  |  | 15,000.00 |  | UNICEF |  | At least 100 new PWDs identified and registered on District Database |  |  |  |  | MELR-CLU |  | UNICEF – CP |
| 58. |  |  |  | Support LEAP programmes in the District | District wide |  |  |  |  | 30,000.00 |  | UNICEF |  | At least three Organizations of PWDs supported to hold zonal meetings |  |  |  |  | DCPC / GES |  | UNICEF – CP |
| 59. |  |  |  | Organize Disability Fund Management Committee Meetings & Other Administrative costs | District office |  |  |  |  | 15,000.00 |  | UNICEF |  | Meeting orgainzed |  |  |  |  | ICI / MELR-CLU |  | UNICEF |
| 60. |  |  |  | Conduct 2 Review Meetings with stakeholders & partners on Child Protection and ISS to enhance inter-sectoral collaboration | District wide |  |  |  |  | 3,000.00 |  | UNICEF |  | At least 10 market swoops in large market centres organised to rescue children engaged in child labour |  |  |  |  | DCPC/ FP |  | UNICEF |
| 61. |  |  |  | Identification and follow-up on delinquent/truant school children to improve enrolment/ retention | District wide |  |  |  |  | 7,000.00 |  | UNICEF |  | office Equipment & stationery procured for Effective service Delivery |  |  |  |  | UNICEF - Comms |  |  |
| 62. |  |  |  | Procure office Furniture, Equipment & stationery to enhance office Administrative Activities | District wide |  |  |  |  | 1,500.00 |  | GOG DACF |  | Enhance office administration of the PWDs |  |  |  |  |  | SWCD | Central Admin |
| 63. | P2: SOCIAL SERVICES DELIVERY | SP2.3: Education & Youth Services |  | Registration of new PWDs onto district Album and database | Some selected public Basic Schools |  |  |  |  | 200,000.00 |  | DACF |  | Enhance the database of the PWDs |  |  |  |  |  | SWCD | Central Admin. |
| 64. |  |  |  | Organize Inter-school competitions | District Office |  |  |  |  | 10,000. 00 |  | IGF |  | Improve student networking , and encourage health competition |  |  |  |  |  | Education Directorate | Central Admin. |
| 65. |  |  |  | Organize District school Performance Appraisal Meeting(SPAM) for basic schools | Coaltar |  |  |  |  | 5,000. 00 |  | IGF |  | Improve quality assurance of activities |  |  |  |  |  | Education Directorate | Central Admin/GES |
| 66. |  |  |  | Train PWDs in income generating activities (IGAs) (i.e. soap making, batik making, handicraft, etc.) | Public and private schools |  |  |  |  | 5,000.00 |  | DACF |  | Empower the PWDs to be self reliance |  |  |  |  |  | SWCD | UNICEF,AyDA/DPCU |
| 67. |  |  |  | Support PWDs Federation activities | District wide |  |  |  |  | 5,000.00 |  |  |  | Improve quality assurance |  |  |  |  |  | Education Directorat e | Central Admin |
| 68. | P2: SOCIAL SERVICES |  | SP2.4:Health services delivery | Train staff on CMAM | District Office |  |  |  |  | 13,05 0.0 0 | DACF |  | Improve on nutritional status of people |  |  |  |  |  |  | Health Directorate | USAID/WHO |
| 69 |  |  |  | Support LED through rapid needs assessment to inform building process through training and re-tooling where necessary of new and existing businesses to enhance job creation | District Office |  |  |  |  | 25,000.00 | IGF |  | Promote business accessibility among PWDs |  |  |  |  |  |  | SWCD | UNICEF |
| 70. |  |  |  | Technical support visits to CHNPS Zones | District wide |  |  |  |  | 8840. 00 |  |  | Improve on revenue generation and data management |  |  |  |  |  |  | Health Directorate | GHS &MOH |
| 71 |  |  |  | Monthly DHMT meeting with stakeholders & partners | District Office |  |  |  |  | 12,000.00 | IGF |  | Improve efficiency in governance & management of the health system |  |  |  |  |  |  | Health Directorate |  |
| 72. |  |  |  | Outreach visits to communities with LEAP households | Asuboi |  |  |  |  | 4,000.00 | DACF |  | To evaluate the impact of LEAP in the district |  |  |  |  |  |  | SWCD | UNICEF |
| 73. |  |  |  | Create awareness on the benefits of LLIN usage, how to assess them in the district | District wide |  |  |  |  | 25,000.00 | DACF |  | Preventing Malaria |  |  |  |  |  |  | Health Directorate | GHS |
| 74. |  |  |  | Organize quarterly community durbars on family planning services, health issue advocacy meetings with opinion leaders, community members and stakeholders | District wide |  |  |  |  | 45,000.00 | IGF |  | Health Awareness Creation |  |  |  |  |  |  | Health Directorate | DFID, World Bank |
| 75. |  |  |  | Procure and supply 500 number mono desk and 400 dual desk to support BECE | District wide |  |  |  |  | 80,000.00 | IGF |  | To promote access to education |  |  |  |  |  |  | Education | GES |
| 76. |  |  |  | Procure and supply 20 office desk to support Health Centres | District wide |  |  |  |  | 150,000 | IGF |  | Refurbish the health facilities for efficient healthcare delivery |  |  |  |  |  |  | Health Directorate | NMCP |
| 77. |  |  |  | Organise adolescent/ youth health forum and provide training for service providers and peer educators on adolescent health issues health education durbars |  |  |  |  |  | 30,000.00 | IGF |  | To prevent teenage pregnancy among adolescent/youth |  |  |  |  |  |  | Health Directorate | Adolescent ambassadors |

| DEVELOPMENT DIMENSION : ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Progr amme (PBB) | Sub- programme( PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCES(GHȻ) |  | INDICATORS (IMPACT/OUTPUT) | Programme Status |  | Implementing Institution/Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | New | Ongoi ng | Lead | Collaborating |
| 78. | P3: INFRASTRUCTURE DELIVERY AND MANAGEMENT | SP3.2: Public Works, and Water Management t | Construction of 1 number CHPS compound at Yakoko | Yakoko |  |  |  |  | 545,000 | DACF | Improve access to healthcare |  |  | Works Dept. | Central Admin |
| 79. |  |  | construction of 1 no. 3 unit KG block at Bepoase | Bepoase |  |  |  |  | 549,000.00 | DACF | Improve access to education |  |  | Works Dept. | Central Admin |
| 80. |  |  | Construction and mechanization of 11 number boreholes with overhead tanks | Krabokese, Obowansane, Yawdonkor, Akuffokrom, Apauwawase, Mankrong, coaltar, Ntowkrom, Kofipare, Amponsahene, Besease |  |  |  |  | 1,001,000 | DACF/RFG VII | Provide access to portable water |  |  | Works Dept. | Central Admin |
| 81. |  |  | Construction of 8 seater toilet facility at Krabokese | Krabokese |  |  |  |  | 449,971.00 | DACF | Improve sanitation |  |  | Works Dept. | Central Admin |
| 82. |  |  | Construction of 3 unit JHS block at Sowatey | Sowatey |  |  |  |  | 546,000.00 | DACF | Improve access to education |  |  | Works Dept. | Central Admin |
|  |  |  | Preparation of screening forms for 2025 planned infrastructure projects | In all the communities with physical project |  |  |  |  | 20,000 |  | To provide detailed analysis and data for all the physical projects |  |  | DPCU | Central Admin |
|  |  |  | Construction of 1NO. six (6) unit classroom with 8-seater WC toilet at Yaw Donkor | Yaw Donkor |  |  |  |  |  | SIF | Improve sanitation |  |  | Works Dept. | Central Admin |
|  |  |  | Construction of 1NO. Four staff quarters and a mechanized borehole at Coaltar | Coaltar |  |  |  |  | 400,000.`00 | SIF | Improve access to staff accommodation |  |  | Works Dept. | Central Admin |
| 83. |  |  | Reclaimation of 25acre land with coconut plantation at Kofipare | Kyenkularbi |  |  |  |  | 100,000 |  | Afforestation |  |  | Works Dept. | Central Admin |
| 84. |  |  | Reclaimation of 25acre land with oil palm plantation at Apau wawase | District Offices/Assets |  |  |  |  | 120,000 | DACF/IGF | Afforestation |  |  | Works Dept. | DEHO |
| 85. |  |  | Construction 10-seater W/C Toilet and Mechanized borehole at Coaltar | Coaltar |  |  |  |  |  | DACF | Improve upon sanitation |  |  | Works | AyDA/Planning |
| 86. |  |  | Construction of 900mmx900mm Con. U Drain, L-200m at Kyekyewere | Kyekyewere |  |  |  |  |  | DACF | Improve drainage system |  |  | Works Dept. |  |
| 87. |  |  | Construction of new DCE Bungalow at Kyekyewere | Kyekyewere |  |  |  |  |  | DACF | Improve staff accommodation |  |  | Works Dept. |  |
| 88. |  |  | Under take street Naming and Property Addressing exercise in 5 communities | 5 selected communities |  |  |  |  | 400,000 | DACF | Improve navigation and accessibility |  |  | PPD | Works Department |
| 89. |  |  | Organize SAT and Technical Planning meetings to approve building permits | District Assembly Office |  |  |  |  | 54,000 | IGF | To assess the effectiveness of permitting |  |  | PPD | Lands Commission/TSC/SPC |

| 90. | INFRASTRUCTURE DELIVERY AND MANAGEMENT | SP3.3: SPATIAL PLANNING | Carry out sensitization and educate to improve upon the permitting system | District wide |  |  |  |  | 2,000.00 | IGF | To increase awareness and improve compliance |  |  | PPD | NCCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 91. |  |  | Rehabilitation of 3.0km Feeder road from teacher Mante to Nodjo | District wide |  |  |  |  | 350,000. | DACF/ IGF | Improve accessibility to road network |  |  | Works Dept. | Central Admin |
| 92. |  |  | Carry out sensitization on road safety measures for Dorkorchiwa GPRTU | Dorkorchiwa |  |  |  |  | 350,000. | DACF/ IGF | Improve safety measures |  |  | Works Dept. | Central Admin |

+

| DEVELOPMENT DIMENSION : EMERGENCY PLANNING AND RESPONSE ( INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Progr amme (PBB) | Sub- programme (PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCES (GHC) |  | INDICATORS | Programme Status |  | Implementing Institution/ Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | New | Ongoing | Lead | Collabo. |
| 93. | P5: ENVIRONMENTAL MANAGEMENT | SP5.1: Disaster Prevention and Management | Awareness creation and sensitization on causes and effects of Fire disasters | In fire prone zones |  |  |  |  |  | DACF | Awareness creation on disaster management |  |  | NADM O | GNFS |
| 94. |  |  | Public Education on Flood, Diseases and Epidemics. | In disaster prone areas |  |  |  |  |  | DACF | Awareness creation on disaster management |  |  | NADM O | DEHU District Health Directorate. |
| 95. |  |  | Education on rainstorm disaster. Identification of flood prone areas. | District wide |  |  |  |  | 4,000 | DACF | Awareness creation on disaster management |  |  | NADM O | District Agric Dept. |
| 96. |  |  | International Disaster Risk Reduction Week | Coaltar |  |  |  |  | 15,000 | DACF | Awareness creation on disaster management |  |  | NADMO | District Assembly |
| 97. |  |  | Creation & Monitoring of DVGs and activities | District wide |  |  |  |  | 20,000 | DACF | To evaluate DVGs |  |  | NADMO |  |
| 98. |  |  | Inspection of fuel stations and industries | District wide |  |  |  |  | 3.000 | DACF | To ensure compliance with compliance, environmental protection and ensuring safety |  |  | NADMO | PPD, WKS, Fin Depts. |
| 99. |  |  | Sensitizing citizens on climate change, energy | District wide |  |  |  |  | 5,000 | DACF | No. of communities sensitized. |  |  | NADMO | Energy Commission |