2025 ANNUAL ACTION PLAN

| DEVELOPMENT DIMENSION : GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Program me(PBB) | Sub- programm e(PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCE GH(Ȼ) |  | INDICATORS (output/impact) | Programme Status |  | Implementing Institution/Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | new | On going | Lead | Collaborating |
| 1. | P4: MANAGEMENT AND ADMINISTRATION | SP4.1: General Administration | Celebration of National Events (Farmers day, May day) | District wide |  |  |  |  | 20,000.00 | DACF | Celebration of day |  |   | Central Admin | All Departments |
| 2. |  |  | Coordinate the organization of quarterly statutory meetings- General Assembly Meetings Management Meetings | District Office |  |  |  |  |  | DACF | Decisions taken |  |    | Central Admin | All Departments All stakeholders |
| 3. |  |  | Printing of bills | District Office |  |  |  |  | 3,600.00 | IGF | No. of Bills printed |    |  | MIS | Finance Depart. |
| 4. |  |  | Maintenance and repair of IT equipment | District Office |  |  |  |  | 1,800.00 | IGF | Efficient operation of equipment |  |  | MIS | Central Admin. |
| 5. |  |  | Website maintenance and updating | District Office |  |  |  |  | 2,500.00 | IGF | Efficient functioning of website |  |  | MIS | All Departments &Units |
| 6. |  |  | Preparation of Procurement Plan for 2026 | District Office |  |  |  |  | 3,000.00 | DACF | Procurement plan |  |  | Procurem ent Dept. | Central Admin. Budget Unit |
| 7. |  |  | Procurement of Office Logistics | District Office |  |  |  |  | 80,000.00 | DACF | No. of logistics |  |  | Procurement Dept. | All Departments &Units HR |
| 8 |  |  | Procurement of 1NO. Projector for the district planning coordinating unit | Planning |  |  |  |  | 8,000.00 | DPATVII | Efficient operation of the unit |  |  |  | Development planning unit |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Procurement of 2NO. laptops for district planning unit | Planning unit |  |  |  |  | 17,000.00 | DPATVII | Efficient operation of the unit |  |  |  | Development planning unit |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Procurement of steel cabinets for the District Registry unit | Registry |  |  |  |  | 16,000.00 | DPATVII | Efficient operation of the unit |  |  |  | Registry unit |
| 11. |  |  | Sensitize the public on revenue mobilization | Entire District |  |  |  |  | 5,000.00 | GOG | Revenue realized |  |  | Budget Dept. | Finance Dept. NCCE |
| 12. |  |  | Public Education on Sanitation | District wide |  |  |  |  | 1,000.00 | IGF | No. of people educated |  |  | NCCE | DEHU, NADMO |
| 13 |  |  | Ensure periodic update on Assembly’s social media platforms | District Office |  |  |  |  | 1,000.00 | IGF | Updates of the platforms |  |   | MIS | Central Admin. |
| 14 |  |  | Public Education on District Level Election/Citizenship | District Office |  |  |  |  | 3,000.00 | IGF | No. of people educated |  |  | NCCE | Central Admin. |
| 15 |  |  | Public Education on Teenage Pregnancy/Child Protection | District wide |  |  |  |  | 3,000.00 | GOG | No. of people educated. |  |  | NCCE | Social Welfare and Community Development |
| 16 |  |  | ARAP Social auditing | District wide |  |  |  |  | 1,500.00 | IGF |  |   |  | NCCE | Agric Dept. Central Admin. |
| 17. |  |  | Implement 2025 capacity building plan | District Office |  |  |  |  | 45,000.00 | DACF | Improve Human resources |  |   | HR | Central Admin |
| 19. |  |  | Purchase Office Stationary/logistics | District Office |  |  |  |  | 6,000.00 | DACF | No. of stationary bought. |  |  | HR | Central Admin. |
| 20. |  |  | Prepare quarterly and annual progress Reports | District Office |  |  |  |  | 3,500.00 | DACF | Reports |  |  | DPCU | All Departments &Units |
| 21. |  |  | Organize quarterly Statutory committee meetings | District Office |  |  |  |  | 50,000.00 | DACF | No. of meetings organized |   |   |  | Central Admin |
| 22 |  |  | Organize quarterly monitoring and evaluatio | District Office |  |  |  |  | 120,000.00 | DACF | No. M and E Ooagnized |  |  | DPCU | Central Admin. |
| 23. |  |  | Prepare 2026 Annual Action Plan. | District Office |  |  |  |  | 5,000.00 | DACF | For planning and development |   |  | DPCU | All Departments & Units |
| 24 |  |  | Prepare 2026- 2029 Medium Term Development Plan | District Office |  |  |  |  | 84,000 | DACF | For planning and development |  |  | DPCU | All Departments & Units |
|  |  |  | Prepare project concept notes for 2025 physical infrastructure projects |  |  |  |  |  | 50,000 | DACF | For planning and development |  |  | DPCU | All Departments & Units |
| 25. |  |  | Organize 2 no.Town Hall Meetings | District wide |  |  |  |  | 10,000.00 | DACF | Improve governance and accountability |  |   | DPCU | Community stakeholders |
| 26. | P4: MANAGEMENT AND ADMINISTRATION |  | Organize fee fixing stakeholders meeting and prepare 2026 composite budget | District Office |  |  |  |  | 30,000.00 | DACF | For budgeting and revenue collection |  |  | Budget Unit | DPCU |
| 27. |  | SP4.1: General Administration | Conduct socio-economic and administrative data collection | District wide |  |  |  |  | 10,00 0 | DACF | For decision making and development |  |  | Statistics Dept. | All Departments & Units |
| 28. |  |  | Data collection activities in preparation of the Assembly's Annual Progress Report | District wide |  |  |  |  | 3,00 0.00 | DACF | To track progress in the district |  |  | Statistics Dept. | DPCU |
| 29. |  |  | Terminal Evaluation of the socio-economic impact of the District Assembly on the lives of the people 10 years after its establishment | District wide |  |  |  |  | 8,00.00 | DACF | For decision making for the next years |  |  | Statistics Dept. | DPCU |
| 30. |  |  | Data collection on teenage pregnancy; causes and implications for the development of the district | District wide |  |  |  |  | 4,000.00 | DACF | To help control teenage pregnacy |  |  | Statistics Dept. | Social Welfare and Community Development |
| 31. |  |  | Data gathering on hospitality facilities in the district | Locations of institutions |  |  |  |  | 2,000.00 | DACF | For revenue mapping |  |  | Statistics Dept. | Budget & Finance Depts. |
| 32. |  |  | Undertake revenue sensitization for rate payers | District wide |  |  |  |  | 10,000.00 | IGF | To improve citizen understanding of taxes |  |  | Finance Dept. | Budget |
| 33. |  |  | Validation, printing and distribution of Bills | District wide |  |  |  |  | 2,000.00 | IGF | Accountability and information giving |  |  | Finance Dept. | MIS, Budget Depts. |
| 34. |  |  | Monitor revenue collection quarterly. | District wide |  |  |  |  | 1,000.00 | IGF | Financial accountability |  |  | Finance Dept. | Internal Audit Monitoring Team |
| 35. |  |  | Collect data and update database of businesses in the District | District wide |  |  |  |  | 3,000.00 | IGF | Enhance revenue projections |  |  | Finance Dept. | Budget Unit |
| 36. |  |  | Internal Security Operations | District Office |  |  |  |  | 20,000.00 | DACF | Enhance public security |  |  | DISEC | Consultants, Central Admin |
| 37. |  |  | Monitoring and Evaluation of Programmes and Projects quarterly. | District wide |  |  |  |  | 30,000.00 | DACF | Ensure efficient use of resources |  |  | DPCU | Stakeholders, Assembly members, community members. |
| 38. |  |  | Legislative enactment and oversight | District Office |  |  |  |  | 20,000.00 | DACF | Increase participation in local governance |  |  | Central Admin. | Legislative committee members |
| 39. |  |  | Support District sub-structures | District wide |  |  |  |  | 5,000.00 | DACF | Increase participation in local governance |  |  | Central Admin. | Stakeholders |
| 40. |  |  | National Service Personnel Support | District Office |  |  |  |  | 40,000.00 | IGF | Human resource strengthening |  |  | Central Admin |  |
| 41. |  |  | GIFMIS Operations | District Office |  |  |  |  | 50,000.00 | IGF | Increase value for money |  |  | Fin. Dept. | Revenue collectors, unit committee members |
| 42. |  |  | Audit Committee & Work Plan | District Office |  |  |  |  | 30,000.00 | DACF | Increase productivity and accountability. |  |  | Internal Audit | Finance Dept., stakeholders |
| 43. |  |  | Maintenance of vehicles | District Office |  |  |  |  | 7,500.00 | IGF | Improve Transport |  |  | Central Admin |  |
| 44. |  |  | Organize quarterly workshops for Transport operators on road safety measures. | District Office |  |  |  |  | 10,000.00 | IGF | Improve safety on the roads/people |  |  | Works Dept. | DPCU, Drivers Consultants |
| 45. |  |  | Data Collection of water facilities within the district. | District wide |  |  |  |  | 5,000.00 | IGF | Data collection for decision making |  |  | Statistics | DPCU |
| 46. |  |  | Revision of 2025 AAP | District Office |  |  |  |  | 2,000.00 | DACF | Governance and accountability |  |  | DPCU |  |

| DEVELOPMENT DIMENSION:ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Program me (PBB) | Sub- programm e(PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCE(GHȻ) |  | INDICATORS (OUTPUT/IMPACT | Programme Status |  | Implementing Institution/Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | New | Ongoi ng | Lead | Collaborating |
| 47. | ECONOMIC DEVELOPMENT SDGs GOAL 8: Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all P1:ECONO MIC DEVELOPM ENT | SP1.1: Trade, Industry and Tourism Services SP1.2:Agri culture Services and Management | Organize 4 No. Local Economic Development meetings | District Office |  |  |  |  | 6,000. 00 | DACF | Improve local economic development |  |  | DPCU | Municipal Planning Coordinating Unit |
| 48 |  |  | Organize 6 farmer fora and sensitization on flagship programs and climate change. | Sowatey, Alafia, Obouho, Oparekrom , Pepoase, Marfokrom |  |  |  |  | 3,000.00 | DACF GOG | No. of farmers in attendance |  |  | Agric. Dept | Central Admin, Farmers |
| 49. |  |  | Organize 1 RELC Session for stakeholders | District Office |  |  |  |  | 7,550.00 | DACF Donor | Stakeholders in Agric engagement |  |  | Agric Dept. | Central Admin., Stakeholders |
| 50. |  |  | Train youth interested in TVET | District Office |  |  |  |  | 12,000. 00 | DACF | Increase job opportunities |  |  | DPCU | SWCD GEA |
| 51. |  |  | Organize meetings and field visits to local Industries | District wide |  |  |  |  | 3,000 | IGF | Enhance cooperation between industries and the assembly |  |  | DPCU | Central Admin. |
| 52. |  |  | Support Tourism Development | District wide |  |  |  |  | 5,000 | DACF | To generate new revenue points |  |  | DPCU | Central Admin |
|  |  |  | 20-25 acres of oil palm plantation | Apau wawase |  |  |  |  |  | Safety Net | Poverty alleviation |  |  | Agric dept. | Central admin |
| 53 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 54 |  |  | Organize one Farmers Day celebration by December 2025 | District wide |  |  |  |  | 70,000.00 | DACF | Appreciate the worth of farmers |  |  | Agric. Dept. | Central Admin. |
| 55 |  |  | 20 acres of coconut plantation | Kofi Pare |  |  |  |  |  | Safety Net | Poverty alleviation |  |  |  |  |
| 56 |  |  | Monthly Technical Review Meetings | District Office |  |  |  |  | 1,700.00 | DACF- MAG | Efficient assessment |  |  | Agric. Depart. | MAG EXT |
| 57 | SDG Target 8.3: Promote development oriented policies that support productive activities, decent job creation, entrepreneurship, creativity and innovation, and encourage the formalization and Growth of micro, small and medium sized enterprises, including through access to financial services |  | Quarterly monitoring visits of selected activities and PERD | District Office |  |  |  |  | 8,000.00 | DACF- MAG | To track progress of PERD |  |  | Agric. Dept. | MAG/MOFA |
| 58. |  |  | Conduct Multi Round Annual Crops and Livestock Survey (MRACLS) | District wide |  |  |  |  | 1,000.00 | IGF | To track progress of crops and livestock |  |  | Agric. Dept. | MAG/MOFA |
| 59. |  |  | Provide direct extension services to 35,000 farmers | District wide |  |  |  |  | 40,800.00 | DACF | To support Agric. production in the district |  |  | Agric Dept. | MOFA |
| 60. |  |  | Establish maize , sweet potato, rice , yam and vegetables demonstrations in 14 farming communities in the district on crop varieties, conservation agriculture, nutrient management, and good agricultural practices | Coaltar, Marfokrom, Mfranor, Asuboi, Afro-Agyei, Kofipare Agbodzi |  |  |  |  | 5,500 | DACF | Demonstration farms established |  |  | Agric. Dept. | MOFA |
| 61. |  |  | Vaccinate 15,000 sheep and goats against PPR disease | District wide |  |  |  |  | 2,000.00 | DACF | Increase access to veterinary services |  |  | Agric. Dept. |  |
| 62 |  |  | Sensitize and train 100 farmers on climate smart agriculture. | District wide |  |  |  |  | 1,200.00 |  | Increase access to extension services |  |  | Agric. Dept. |  |
| 63. |  |  | Monitor and train 200 farmers on Good Agricultural Practices in oil palm plantation management under the Planting for Export and Rural Development, (PERD | District wide |  |  |  |  | 930.00 | DACF | Increased access to extension services |  |  | Agric. Dept. | MAG/MOFA |
| 64. |  |  | Train 400 farmers on safe-use of Agro- chemicals by | District Office |  |  |  |  | 2,000.00 | DONOR | Increase knowledge of safety percussion on agro-chemical usage |  |  | Agric. Dept. | NGO |
| 65. |  |  | Conduct monthly intensive disease surveillance on poultry and livestock. | Entire District |  |  |  |  | 3,600.00 | Donor | Enhanced surveillance and prevention of animal pest and disease. |  |  | Agric Dept. | NGO |
| 66. |  |  | Surveillance and awareness creation and facilitate the control of Fall Army Worm (FAW) | Entire District |  |  |  |  | 1,500.00 | Donor | Promote access to plant disease prevention and control methods |  |  | Agric. Dept. | NGO |
| 67. |  |  | Facilitate the establishment of 2 satellite Markets for gari sales. | Amanase, Asuboi |  |  |  |  | 1,500.0 0 | IGF | Farmers linked to agricultural markets and department of Agriculture |  |  | Agric. Depart. | MAG |
| 68. |  |  | Participate in Eastern commodity fair |  |  |  |  |  | 4,000. 00 | DACF/Donor | Farmers linked to agricultural markets and investors |  |  | Agric. Dept. | PPD NADMO |
| 69. |  |  | Train women gari processing groups on hygiene at processing site | Aboabo, Asuboi, Agodza, Amanase, Mankron |  |  |  |  | 10,000. 00 | IGF | Enhance good hygiene at processing site |  |  | Agric. Dept. | SWCD PPD NADMO |
| 70. |  |  | Train 150 farmers and processors on food safety with emphases on how to avoid contaminations | Aboabo, Asuboi, Agodza, Amanase, Mankron |  |  |  |  | 7,0000. 00 | DACF | Commodity grades and standards developed for quality assurance |  |  | Agric. Dept. | Statistics Dept. |
| 71. |  |  | Facilitate the formation of 8 new FBOs and train 50 new and existing FBOs in group dynamics and cohesion | District wide |  |  |  |  | 8,000.0 0 | DACF | Increase efficiency and productivity |  |  | Agric. Dept. |  |
| 72. |  |  | Build capacity of women processors FBOs in value addition and negotiation skills | District wide |  |  |  |  | 3,000.00 | Donor | Establishing functional agricultural Apex industry |  |  | Agric. Dept. | NBSSI |
| 73. |  |  | Train 2 women groups and 5 basic schools on back-yard and school gardening | Aboabo, Asuboi, Agodza, Amanase, Mankron, Anum Apapam, Sowatey |  |  |  |  | 4,840.00 | Donor | Improve economic capacities of women |  |  | Agric. Dept. | MOFA |
| 74. |  |  | Organize quarterly Business fora | District Office |  |  |  |  | 10,000.00 | DACF/IGF | Enhance business cooperation |  |  | GEA | DPCU Businesses |
| 75. |  |  | Conduct LED community profiling for 10 selected communities | 10 selected communities |  |  |  |  | 2,000.00 | DACF | Improve economic development |  |  | GEA | DPCU |
| 76 |  |  | Support LED through rapid needs assessment to inform building process through training and re-tooling where necessary of new and existing businesses to enhance job creation | District wide |  |  |  |  | 4,000.00 | DACF | Improve economic development |  |  | GEA | DPCU |

| DEVELOPMENT DIMENSION : SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Program me (PBB) | Sub- programm e(PBB) |  | Broad Activities | Location | Timeframe |  |  |  | FINANCE(GHȻ) |  |  |  | INDICATORS (OUTPUT/IMPACT) | Programme Status |  |  |  | Implementing Institution/Department |  |  |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST |  | SOURCE |  |  | New |  | Ong oing |  | Lead |  | Collaborating |
| 77. | P2: SOCIAL SERVICES DELIVERY | SP2.1: Environmental Health and Sanitation Services |  | Organize quarterly clean up exercises. | District wide |  |  |  |  | 6,800.00 |  | GOG |  | Clean-up exercise carried out |  |  |  |  | EHSU |  | Zoomlion, NADMO |
| 78. |  |  |  | Collect data on all CSOs and private sector enterprises active in the district | Selected communities |  |  |  |  | 8,700.00 |  | UNICEF |  | Effective participation of CSOs and private sector entreprises within the district |  |  |  |  | DCPC |  | DBO/DPCU |
| 79. |  |  |  | Organize meeting with management of identified CSOs and private sector enterprises and foster discussions to learn about respective strategies to help eliminate child labour and possible avenues for collaboration | Selected communities |  |  |  |  | 9,500.00 |  | UNICEF |  | To help eliminate child labour and possible aveneues for collaboration |  |  |  |  | DCPC |  | Identified CSOs / Private Enterprises |
| 80. |  |  |  | Establish a platform for engagement and knowledge sharing among district level CSOs/ private enterprises. | Selected communities |  |  |  |  | 2,000.00 |  | UNICEF |  | Sharing of knowledge amongst stakeholders to facilitate development in the district |  |  |  |  | FP |  | Identified CSOs / Private Enterprises |
| 81. |  |  |  | Organize bi-annual district level stakeholders review meeting among government institutions and stakeholders within district. | District wide |  |  |  |  | 6,000.00 |  | UNICEF |  | Foster unity amongst stakeholders and development within the district |  |  |  |  | DCPC |  | UNICEF – CP |
| 82. |  |  |  | Organize training for DCPC members on integrated planning, budgeting, monitoring and reporting | District office |  |  |  |  | 4,500.00 |  | UNICEF |  | Capacity building amongst stakeholders for development |  |  |  |  | DCPC |  | UNICEF – SPI |
| 83. |  |  |  | Organize an orientation for DPCU Members on Child Labour issues in district and need to tackle it holistically | District office |  |  |  |  | 4,700.00 |  | UNICEF |  | Strategies to tackle Child labour issues holistically |  |  |  |  | DCPC |  | UNICEF - SPI |
| 84. |  |  |  | Support to organize stakeholders engagement for organization of district APR | Selected communities |  |  |  |  | 10,000.00 |  | UNICEF |  | Strategies to enhance the District APR through stakeholders engagement |  |  |  |  | DPCU |  | UNICEF - SPI |
| 85. |  |  |  | Organize town hall to discuss AAP Composite budget and APR and receive feedback from community members | District office |  |  |  |  | 12,000.00 |  | UNICEF |  | Strategies to enhance budget, programmes and projects within the District AAP and APR |  |  |  |  | DPCU |  | UNICEF - SPI |
| 86. |  |  |  | Train DCPC members and staff of SWCD on GCLMS | District office |  |  |  |  | 15,000.00 |  | UNICEF |  | Capacity building on GCLMS |  |  |  |  | MELR-CLU |  | UNICEF – CP |
| 87. |  |  |  | Organize a refresher training/coaching for staff of SWCD on SWIMS | District office |  |  |  |  | 15,000.00 |  | UNICEF |  | Capacity building on SWIMS |  |  |  |  | MELR-CLU |  | UNICEF – CP |
| 88. |  |  |  | Undertake district-wide data collection on school enrolment and retention to inform planning; disseminate report | District wide |  |  |  |  | 30,000.00 |  | UNICEF |  | Data collection on school enrolment and retention to inform planning; |  |  |  |  | DCPC / GES |  | UNICEF – CP |
| 89. |  |  |  | Train DCPC and DSWCD officers on use of GCLMS | District office |  |  |  |  | 15,000.00 |  | UNICEF |  | Capacity building on GCLMS |  |  |  |  | ICI / MELR-CLU |  | UNICEF |
| 90. |  |  |  | Keep records of document successes, challenges and best practice at every stage of project implementation; disseminate reports | District wide |  |  |  |  | 3,000.00 |  | UNICEF |  | Track stages of projects through record keeping |  |  |  |  | DCPC/ FP |  | UNICEF |
| 91. |  |  |  | Print and distribute T-shirts and other paraphernalia on Child Labour to DCPC members and partner departments | District wide |  |  |  |  | 7,000.00 |  | UNICEF |  | Publicity on how to eradicate Child Labour |  |  |  |  | UNICEF - Comms |  |  |
| 92. |  |  |  | Print posters and flyers for distribution to school children and community members | District wide |  |  |  |  | 5,000.00 |  | UNICEF |  | Publicity on how to eradicate Child Labour |  |  |  |  | UNICEF - Comms |  |  |
| 93. |  |  |  | Embark on floats/walk with traditional leaders, community members and school children to communicate need to eliminate child labour. | District wide |  |  |  |  | 10,000.00 |  | UNICEF |  | Publicity on how to eradicate Child Labour |  |  |  |  | DCPC/ CCPCs |  | UNICEF – Comms |
| 94 |  |  |  | Develop educational videos and facilitate screening in communities for educational purposes | District wide |  |  |  |  | 20,000.00 |  | UNICEF |  | Publicity on how to eradicate Child Labour |  |  |  |  | UNICEF – Comms/ DCPC/ CCPCs |  | UNICEF – Comms |
| 95. |  |  |  | Undertake community sensitization through community durbars, PTAs, LEAP disbursement meetings, ante and post-natal clinics, and any other focus group meetings on universal, right-age enrolment of children, especially children with disabilities, etc. | District wide |  |  |  |  | 70,000.00 |  | UNICEF |  | Awareness creation on education to help children with disabilities |  |  |  |  | DCPC |  | UNICEF – Edu |
| 96. |  |  |  | Embark on home visits and case follow-ups to identify and deal will cases of child seclusion and refer for the appropriate social services | District wide |  |  |  |  | 65,000.00 |  | UNICEF |  | Strategies to curb child seclusion within the district |  |  |  |  | DCPC/ CCPCs/ SWCDOs/ CHNs |  | UNICEF – Edu |
| 97. |  |  |  | Organize a refresher training for SISOs head teachers and other key educational actors on right age of enrolment, inclusive education, etc. | District wide |  |  |  |  | 50,000.00 |  | UNICEF |  | Capacity building for stakeholders to enhance age of enrolment and inclusive education |  |  |  |  | GES/DCPC |  | UNICEF – Edu |
| 98. |  |  |  | Organize a refresher training for SISOs head teachers and other key educational actors on guidelines on pregnancy and schooling, safe schools, inclusive education, etc. | District wide |  |  |  |  | 50,000.00 |  | UNICEF |  | Capacity building for stakeholders to curb pregnancy in schooling, safe schools and inclusive education |  |  |  |  | GES/DCPC |  | UNICEF – Edu |
| 99. |  |  |  | Embark on home visits and case follow-ups to identify and deal will cases of school drop-outs, teenage mothers, etc., and refer for the appropriate social services | District wide |  |  |  |  | 50,000.00 |  | UNICEF |  | Strategies to curb school drop-outs and teenage mothers within the district |  |  |  |  | DCPC/ CCPCs/ SWCDOs/ CHNs |  | UNICEF – Edu |
| 100. |  |  |  | Organize a training/ refresher training for head teachers, teachers and District Teacher Support Teams (DTST) on Differentiated Learning (DL) instruction, and pedagogy, to support children, especially those who returned to school | District wide |  |  |  |  | 55,000.00 |  | UNICEF |  | Capacity building for stakeholders to support children (returned to school) |  |  |  |  |  |  | UNICEF – Edu |
| 101 |  |  |  | Organize a training on the usage of mSRC for SISOs and other key educational actors | District office |  |  |  |  | 40,000.00 |  | UNICEF |  | Capacity building for stakeholders on usage of Msrc |  |  |  |  | GES/ FP |  | UNICEF – Edu |
| 102 |  |  |  | Organize coaching/ refresher training for officers of DSWCD/ DCPC on the use of SWIMS/ GCLMS. | District office |  |  |  |  | 40,000.00 |  | UNICEF |  | Capacity building for stakeholders on usage of SWIMS/GCLMS |  |  |  |  | RCPC/ UNICEF – CP |  | UNICEF – CP |
| 103 |  |  |  | Support the DED with logistics to enable implementation of DL instruction and pedagogy | District wide |  |  |  |  | 35,000.00 |  | UNICEF |  | Implementation of DL instruction and pedagogy |  |  |  |  |  |  | UNICEF – Edu |
| 104 |  |  |  | Support DSWCD/ DCPC to embark on regular visits to homes/farms/schools/ markets to enable early identification of children in and at risk of child labour | District wide |  |  |  |  | 40,000.00 |  | UNICEF |  | Early identification of children in and at risk of child labour |  |  |  |  | DSWCD/ DCPC |  | UNICEF – CP |
| 105 |  |  |  | Form and train members of CCPCs in at least 20 more communities by end of year | Selected communities |  |  |  |  | 40,000.00 |  | UNICEF |  | Capacity building for members of CCPCs |  |  |  |  | DSWCD/ DCPC |  | UNICEF – CP |
| 106 |  |  |  | Advocate for the establishment of DOVVSU in the district | District wide |  |  |  |  | 5,000.00 |  | UNICEF |  | Establishment of DOVVSU in the district |  |  |  |  | UNICEF - CP |  |  |
| 107 |  |  |  | Train officers of DOVVSU/ police on Child Labour, ISSOPs and handling of juvenile cases | District wide |  |  |  |  | 8,500.00 |  | UNICEF |  | Capacity building for officers of DOVVSU / police on Child Labour, ISSOPs |  |  |  |  | GPS/ UNICEF – CP |  | UNICEF – CP |
| 108 |  |  |  | Support DOVVSU/ Police with logistics to enhance case investigation/ referral | District wide |  |  |  |  | 20,000.00 |  | UNICEF |  | Provision of logistics to enhance case investigation/ referral |  |  |  |  | UNICEF – CP |  |  |
| 109 |  |  |  | Train CCPCs/ DCPC on available social protection programmes and referral protocols | District wide |  |  |  |  | 9,000.00 |  | UNICEF |  | Social protection programmes and referral protocols |  |  |  |  | RCPC/ UNICEF – SP/ DCPC |  | UNICEF – SP |
| 110 |  |  |  | Support CCPCs/ DCPC with logistics to enhance prompt referrals | District wide |  |  |  |  | 20,000.00 |  | UNICEF |  | Provision of logistics to enhance prompt referrals |  |  |  |  | UNICEF – SP/ DCPC |  | UNICEF – SP |
| 111 |  |  |  | Gather comprehensive data on schools enrolled on GSFP in district, current state, and schools not enrolled currently on programme and disseminate information | District wide |  |  |  |  | 17,000.00 |  | UNICEF |  | Comprehensive data collection |  |  |  |  | GES/ DCPC |  | UNICEF – SP |
| 112 |  |  |  | Document and disseminate reports of all activities, including challenges and successes during implementation | District wide |  |  |  |  | 5,000.00 |  | UNICEF |  | Proper documentation and reporting on activities |  |  |  |  | CCPCs/ DCPC |  | UNICEF – CP |
| 113 |  |  |  | Engage/ train all caterers contracted on GSFP on ways of improving system | District wide |  |  |  |  | 9,500.00 |  | UNICEF |  | Train all caterers contracted on GSFP on ways of improving system |  |  |  |  | GES/ DCPC |  | UNICEF – SP |
| 114 |  |  |  | Train DCPC, DSWCD, Police/DOVVSU, Labour Inspectors on ISSOPs, Child | District wide |  |  |  |  | 9,500.00 |  | UNICEF |  | Capacity building for stakeholders |  |  |  |  | UNICEF - CP |  |  |
| 115 |  |  |  | Procure supplies and logistics such as Case files, computers, printer, router, furniture, etc. to enhance smooth running of office and cases handling and referrals | District office |  |  |  |  | 10,000.00 |  | UNICEF |  | Procurement of logistics for smooth running of office, cases handling and referrals |  |  |  |  | UNICEF – CP |  |  |
| 116 |  |  |  | Procure supplies and logistics such as flipchart stand, projector, etc. for training, video screening sessions and community sensitization activities. | District office |  |  |  |  | 10,000.00 |  | UNICEF |  | Procurement of logistics for video screening sessions and community sensitization activities |  |  |  |  | UNICEF – CP |  |  |
| 117 |  |  |  | As a long-term measure, the project should advocate for the provision of a vehicle for DSWCD/ DCPC to enhance referral/ field activities. | District office |  |  |  |  | 300,000.00 |  | UNICEF |  | provision of a vehicle for DSWCD/ DCPC to enhance referral/ field activities. |  |  |  |  | UNICEF – CP |  | All Partners |
| 118 |  |  |  | Provide TnT/fuel, DSA for RCPC to offer supervision and coaching support to district/community frontline workers | District wide |  |  |  |  | 10,000.00 |  | UNICEF |  | Supervision and coaching support to district/community frontline workers |  |  |  |  | UNICEF – CP |  |  |
| 119 |  |  |  | Gather comprehensive data on all cocoa companies active in district | Selected communities |  |  |  |  | 20,000.00 |  | UNICEF |  | Data collection on cocoa companies within the district |  |  |  |  | DCPC/ CCPCs |  | UNICEF |
| 120 |  |  |  | Conduct orientation sessions for identified companies, farmers and women organizations on referral pathways and reporting mechanisms in child labour cases. | Selected communities |  |  |  |  | 22,000.00 |  | UNICEF |  | Capacity building for stakeholders on referral pathways and reporting mechanisms in child labour |  |  |  |  | DCPC |  | UNICEF |
| 121 |  |  |  | Form/ strengthen community health committees (CHCs) in at least 50 communities by end of year | Selected communities |  |  |  |  | 50,000.00 |  | UNICEF |  | Strengthen community health committees (CHCs) |  |  |  |  | GHS/ DCPC |  | UNICEF - SP |
| 122. |  |  |  | Train all CHCs on case identification and referral protocols | Selected communities |  |  |  |  | 30,000.00 |  | UNICEF |  | Capacity building |  |  |  |  | GES/ DCPC |  | UNICEF - SP |
| 123. |  |  |  | Establish LEAP Beneficiary Welfare Association (LBWA) in at least 10 pay point communities | Selected communities |  |  |  |  | 30,000.00 |  | UNICEF |  | Establishment of LEAP Beneficiary Welfare Association |  |  |  |  | DSWCD/ DCPC |  | UNICEF - SP |
| 124. |  |  |  | Train LBWAs on LEAP co-responsibilities to champion advocacy against child labour at the local level. | Selected communities |  |  |  |  | 30,000.00 |  | UNICEF |  | Advocacy against child labour at the local level |  |  |  |  | DSWCD/ DCPC |  | LMS/ UNICEF – SP |
| 125. |  |  |  | Organize training for members of DEOC to build their capacity to effectively play a supervisory role in education delivery | Selected communities |  |  |  |  | 30,000.00 |  | UNICEF |  | Supervision in education delivery |  |  |  |  | UNICEF – Edu |  |  |
| 126. |  |  |  | Organize training/ capacity building workshops for SMC/PTA in selected communities across the district to champion advocacy against child labour at the local level and improve outcomes | Selected communities |  |  |  |  | 15,000.00 |  | UNICEF |  | Advocacy against child labour at the local level and improve outcomes |  |  |  |  | GES/ DEOC |  | UNICEF – Edu |
| 127. |  |  |  | Organize at least two planning and two review meetings with particular focus on SPAMS, SPIP and ADEOP | District office |  |  |  |  | 9,000.00 |  | UNICEF |  | Capacity building on SPAMS, SPIP and ADEOP |  |  |  |  | GES |  | UNICEF – Edu |
| 128. |  |  |  | Form/strengthen CCPCs in at least 25 communities across district by end of year | Selected communities |  |  |  |  | 30,000.00 |  | UNICEF |  | Strengthen CCPCs within the district |  |  |  |  | DCPC/ DSWCD |  | UNICEF – CP |
| 129. |  |  |  | Train CCPCs (new and already existing) and other community opinion leaders on use of CP Toolkits | Selected communities |  |  |  |  | 30,000.00 |  | UNICEF |  | Capacity building on the use of CP Toolkits |  |  |  |  | DCPC/ DSWCD |  | UNICEF – CP |
| 130. |  |  |  | Facilitate provision of resources in CP Facilitation toolkits to CCPCs | Selected communities |  |  |  |  | 30,000.00 |  | UNICEF |  | Provision of resources in CP Facilitation toolkits to CCPCs |  |  |  |  | DCPC/ DSWCD |  | UNICEF – CP |
| 131. |  |  |  | Develop videos in local language on human interest stories aimed at influencing positive attitudinal change and eliminating child labour | Selected communities |  |  |  |  | 10,000.00 |  | UNICEF |  | Influencing positive attitudinal change and eliminating child labour |  |  |  |  | UNICEF - SP |  |  |
| 132. |  |  |  | Screen videos across selected communities to initiate discussions around, and mobilize communities to participate fully to eliminate child labour | Selected communities |  |  |  |  | 10,000.00 |  | UNICEF |  | Mobilize communities to participate fully to eliminate child labour |  |  |  |  | DCPC/ CCPC |  | UNICEF – SP |
| 133. |  |  |  | Identify and compile a comprehensive database of potential beneficiaries | Selected communities |  |  |  |  | 10,000.00 |  | UNICEF |  | Compilation of comprehensive database for potential beneficiaries |  |  |  |  | DCPC/ CCPC |  | UNICEF – SP |
| 134. |  |  |  | Assess and refer identified youth to appropriate skills training | Selected communities |  |  |  |  | 10,000.00 |  | UNICEF |  | Skills training for potential youth |  |  |  |  | DCPC/ CCPC |  | UNICEF – SP |
| 135. |  |  |  | Organize a Training of Trainers (ToT) for DCPC/ DSWCD/ DEOC on positive parenting skills | Selected communities |  |  |  |  | 10,000.00 |  |  |  | Capacity building on positive parenting skills |  |  |  |  | UNICEF - CP |  |  |
| 136. |  |  |  | Train CCPCs/SMC/PTA and selected head teachers/ teachers on positive parenting skills | Selected communities |  |  |  |  | 10,000.00 |  |  |  | Capacity building on positive parenting skills |  |  |  |  | DCPC/ GES |  | UNICEF - CP |
| 137. |  |  |  | Organize sensitization programs for parents on positive parenting | Selected communities |  |  |  |  | 10,000.00 |  |  |  | Sensitization on positive parenting skills |  |  |  |  | DCPC/ CCPCs |  | UNICEF - CP |
| 138. |  |  |  | Organize ToT for DSWCD/ DCPC on VSLA | Selected communities |  |  |  |  | 10,000.00 |  |  |  | Capacity building on VSLA |  |  |  |  | UNICEF - SP |  |  |
| 139 |  |  |  | Form VSLAs in selected communities across district by end of year. | Selected communities |  |  |  |  | 10,000.00 |  |  |  | Establishment of VSLA |  |  |  |  | DCPC/ DSWCD |  | UNICEF – SP |
| 140. |  |  |  | Output 2.3 Enhanced capacity of district social welfare and community development, labour inspectors, justice and law enforcement actors, health and education staff, NGOs and business partners on integrated social services approach and definition of clear roles and responsibilities, and referral pathways | District wide |  |  |  |  | 145,000 |  | GOG |  | Health and Sanitation improvement |  |  |  |  | EHSU |  | . Zoomlion |
| 141. |  |  |  | Medical screening and certification of food and drink vendors | District wide |  |  |  |  | 2,800.00 |  | GOG |  | Food vendor screened. |  |  |  |  | EHSU |  | Agric Dept |
| 142. |  |  |  | Leveling of final disposal site at Achiansah | Achiansa |  |  |  |  | 41,500 |  | GOG |  | Health and sanitation improvement |  |  |  |  | EHSU |  | Central Admin. Zoomlion |
| 143. |  |  |  | Fumigation of refuse dumps/public latrines/ Desilting of choked drains | District wide |  |  |  |  | 166,000.00 |  | GOG |  | Environmental health and sanitation improvement |  |  |  |  | EHSU |  | Central Admin. Zoomlion |
| 144. |  |  |  | Organize awareness/education programs on household latrines/Hygiene/ Environment enhancement programs (Air quality control, Noise pollution control, Land restoration/reclamation, environmental education, afforestation etc.) | District communities/schools |  |  |  |  | 3,900.00 |  | IGF |  | Education and awareness of environmental issues |  |  |  |  | EHSU |  | Central Admin , NCCE, NADMO |
| 145. |  |  |  | Interment of unknown dead bodies | District wide |  |  |  |  | 2,500.00 |  | GOG |  | Bodies buried to decluster mortuaries |  |  |  |  |  | EHSU | Undertakers |
| 146. | P2: SOCIAL SERVICES DELIVERY | SP2.2: Social Welfare and Community Services |  | Settle and dispose-off at least 60 family welfare and child maintenance cases. |  |  |  |  |  | 5,000. 00 |  | DACF |  | Improve family welfare and child maintenance system |  |  |  |  |  | SWCD | GES, POLICE, GHS, NGO |
| 147. |  |  |  | Train at least 2 women groups on alternative livelihood activities. (demonstration) | Selected communities |  |  |  |  | 6,000. 00 |  | GOG DACF |  | Empower women economically |  |  |  |  |  | SWCD | NGO |
| 148. |  |  |  | Train and supervise at least 10 Savings & Loans groups (VSLAs) to encourage savings culture among women to ensure economic empowerment (financial inclusion) | Boasi Sibi, Tettenku, Kwaboanta, Mankrong, Ayekokooso, Minimade and other selected communities |  |  |  |  | 4,000.00 |  | GOG DACF |  | Improve financial inclusion and access to credit |  |  |  |  |  | SWCD | SOLIDARIDAD |
| 149. |  |  |  | Train and sensitize at least 2 women groups on group dynamics and entrepreneurial skills | 2 Women Groups |  |  |  |  | 5,000. 00 |  |  |  | Empower women economically |  |  |  |  |  | SWCD | NGO, Central Admin |
| 150. |  |  |  | Sensitize selected communities on domestic violence | Selected communities |  |  |  |  | 30,00 0.00 |  |  |  | Reduce/ mitigate domestic violence |  |  |  |  |  | SWCD | Community Leaders, Central Admin |
| 151. |  |  |  | Train and sensitize at least 2 women groups on gender, power dynamics and support gender related activities | Selected women groups |  |  |  |  | 7,000. 00 |  |  |  | Improve gender mainstreaming |  |  |  |  |  | SWCD | NGO, Central Admin |
| 152. |  |  |  | Mobilize beneficiaries for LEAP payments/Enroll at least 70 new beneficiaries. NHIS Registration | District wide |  |  |  |  | 5,000.00 |  | DACF |  | Increase social protection coverage |  |  |  |  |  | SWCD | Central Admin NHIS |
| 153. | P2: SOCIAL SERVICES DELIVERY | SP2.2: Social Welfare and Community Services/Development |  | Sensitize men’s group on gender based violence and its consequences on families | District wide |  |  |  |  | 8,393.00 |  | GOG DACF |  | Mitigate Gender based violenec |  |  |  |  |  | SWCD | Central Admin |
| 154. |  |  |  | Communtiy Education on child right and protection, child marriage, teenage pregnancy and child labour | District wide |  |  |  |  | 2,500.00 |  | DACF |  | Increase social protection coverage |  |  |  |  |  | SWCD | LEAP Secretariat CLIC Members |
| 155. |  |  |  | Sensitize 10 communities on family welfare and sexual, CCPCs, child labour and gender domestic violence issues | District wide |  |  |  |  | 3,245.00 |  | DACF |  | Improve livelihood support targeting |  |  |  |  |  | SWCD | NGO, AyDA, Solidaridad, CRI |
| 156. |  |  |  | NHIS Registration of about 500 indigents (aged, OVC, PWDs) | District wide |  |  |  |  | 12,00 0.00 |  | DACF |  | Increase livelihood opportunities and income for PWDs |  |  |  |  |  | SWCD | GFD, NHIS, GES, NGO, GHS |
| 157. |  |  |  | Train 100 PWDs in IGA and support other PWDs | District wide |  |  |  |  | 15,000. 00 |  | DACF |  | Increase livelihood opportunities and income for PWDs |  |  |  |  |  | SWCD | AyDA, NGOS, GFD, NBSSI |
| 158. |  |  |  | Coordinate and implement activities on integrated service delivery in (lnter-sectoral social service (ISS) delivery) | District wide |  |  |  |  | 50,00 0.00 |  | DACF |  | Improve inter-sectoral service delivery |  |  |  |  |  | SWCD | ISSOP Committee, NCCE, NGO, AyDA, DOVVSU, GES, GHS, Com’ members |
| 159. |  |  |  | Organize at least 5 mass meetings to sensitize parents and community members on DSWCD and District Assembly programmes and activities | District wide |  |  |  |  | 6,500.00 |  | IGF DACF GOG |  | Increase local participation in Governance |  |  |  |  |  | SWCD | Community Leaders |
| 160. |  |  |  | Monitoring of department’s programmes and activities | District wide |  |  |  |  | 1,500.00 |  | GOG DACF |  | Improve quality assurance of activities |  |  |  |  |  | SWCD | Central Admin |
| 161. | P2: SOCIAL SERVICES DELIVERY | SP2.3: Education & Youth Services |  | Establish ICT laboratories in the Public Basic Schools | Some selected public Basic Schools |  |  |  |  | 200,000.00 |  | DACF |  | Enhance ICT usage at the basic level |  |  |  |  |  | Education Directorate | Central Admin. |
| 162. |  |  |  | Organize Inter-school competitions | District Office |  |  |  |  | 10,000. 00 |  | IGF |  | Improve student networking , and encourage health competition |  |  |  |  |  | Education Directorate | Central Admin. |
| 163. |  |  |  | Organize District school Performance Appraisal Meeting(SPAM) for basic schools | Coaltar |  |  |  |  | 5,000. 00 |  | IGF |  | Improve quality assurance of activities |  |  |  |  |  | Education Directorate | Central Admin/GES |
| 164. |  |  |  | Organize Mock exams for BECE candidates | Public and private schools |  |  |  |  | 5,000.00 |  | DACF |  | Prepare students towards BECE |  |  |  |  |  | Education Directorate | GES |
| 165. |  |  |  | Organize my First Day at school | All public Basic Schools |  |  |  |  | 5,000.00 |  |  |  | Improve quality assurance |  |  |  |  |  | Education Directorat e | Central Admin |
| 166. | P2: SOCIAL SERVICES |  | SP2.4:Health services delivery | Train staff on CMAM | District Office |  |  |  |  | 13,05 0.0 0 | DACF |  | Improve on nutritional status of people |  |  |  |  |  |  | Health Directorate | USAID/WHO |
| 167 |  |  |  | Train 20 CHN'S to become CHO'S | District Office |  |  |  |  | 25,000.00 | IGF |  | Improved capacity for efficient service delivery |  |  |  |  |  |  | Health Directorate | GHS |
| 168 |  |  |  | Technical support visits to CHNPS Zones | District wide |  |  |  |  | 8840. 00 |  |  | Improve on revenue generation and data management |  |  |  |  |  |  | Health Directorate | GHS &MOH |
| 169. |  |  |  | Monthly DHMT meeting with stakeholders & partners | District Office |  |  |  |  | 12,000.00 | IGF |  | Improve efficiency in governance & management of the health system |  |  |  |  |  |  | Health Directorate |  |
| 170. |  |  |  | Upgrade health facilities and provide logistics for all health facilities | Asuboi |  |  |  |  | 12,000.00 | GOG |  | Enhance national capacity for the attainment of the health related SDGs and sustain the gains |  |  |  |  |  |  | Health Directorate | Central Admin/ GHS |
| 171. |  |  |  | Create awareness on the benefits of LLIN usage, how to assess them in the district | District wide |  |  |  |  | 25,000.00 | DACF |  | Preventing Malaria |  |  |  |  |  |  | Health Directorate | GHS |
| 172. |  |  |  | Organize quarterly community durbars on family planning services, health issue advocacy meetings with opinion leaders, community members and stakeholders | District wide |  |  |  |  | 45,000.00 | IGF |  | Health Awareness Creation |  |  |  |  |  |  | Health Directorate | DFID, World Bank |
| 173. |  |  |  | Conduct quarterly visits to prayer camps for active case search | District wide |  |  |  |  | 6,000.00 | IGF |  | Efficient Healthcare delivery |  |  |  |  |  |  | Health Directorate | EPI, WHO |
| 174. |  |  |  | Conduct OTSS monitoring to all facilities | District wide |  |  |  |  | 30,000.00 | IGF |  | Disease prevention& monitoring |  |  |  |  |  |  | Health Directorate | NMCP |
| 175. |  |  |  | Organise adolescent/ youth health forum and provide training for service providers and peer educators on adolescent health issues health education durbars |  |  |  |  |  | 30,000.00 | IGF |  | To prevent teenage pregnancy among adolescent/youth |  |  |  |  |  |  | Health Directorate | Adolescent ambassadors |
| 176 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| DEVELOPMENT DIMENSION : ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Progr amme (PBB) | Sub- programme( PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCES(GHȻ) |  | INDICATORS (IMPACT/OUTPUT) | Programme Status |  | Implementing Institution/Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | New | Ongoi ng | Lead | Collaborating |
| 177. | P3: INFRASTRUCTURE DELIVERY AND MANAGEMENT | SP3.2: Public Works, and Water Management t | Construction of 3.0km feeder road from Teacher Mante - Nodjo | Teacher Mante - Nodjo |  |  |  |  | 157,842.50 | Safety Net | Km of Feeder road constructed |  |  | Works Dept. | Central Admin |
| 178. |  |  | Construction of 1No CHPS Compound with mechanized borehole at Kyekyewere | Kyekyewere |  |  |  |  | 549,000.00 | DACF/RFG VII | Improve access to health care delivery |  |  | Works Dept. | Central Admin |
| 179. |  |  | Drilling and mechanization of 5 no. borehole with overhead tank at Ayibontey, Amanase, Ningo, Obowansane, Yawbaahkrom | Ayibontey, Amanase, Ningo, Obowansane, Yawbaahkrom |  |  |  |  | 335,007.00 | DACF/RFG VII |  |  |  | Works Dept. | Central Admin |
| 180. |  |  | Construction of 1No. 3-unit classroom block at Kwaboanta | Kwaboanta |  |  |  |  | 449,971.00 | DACF/RFG VII |  |  |  | Works Dept. | Central Admin |
| 181. |  |  | Construction of 1 No. four unit staff Quarters with a mechanized borehole at kyekyewere | Kyekyewere |  |  |  |  | 546,000.00 | SIF | Improve upon staff accommodation |  |  | Works Dept. | Central Admin |
|  |  |  | Construction of 900mm x 900mm conc. U-Drain, L=200m at Kyekeyewere | kyekyewere |  |  |  |  |  |  |  |  |  | Works Dept. | Central Admin |
|  |  |  | Construction of 1NO. six (6) unit classroom with 8-seater WC toilet at Yaw Donkor | Yaw Donkor |  |  |  |  |  |  |  |  |  | Works Dept. | Central Admin |
|  |  |  | Construction of 1NO. Four staff quarters and a mechanized borehole at Coaltar | Coaltar |  |  |  |  |  |  |  |  |  | Works Dept. | Central Admin |
| 182. |  |  | Construction of 1 no. six (6)-unit classroom block with 8-seater WC toilet at Kyenkularbi | Kyenkularbi |  |  |  |  |  |  |  |  |  | Works Dept. | Central Admin |
| 183. |  |  | Routine maintenance of office assets | District Offices/Assets |  |  |  |  |  |  |  |  |  | Works Dept. | DEHO |
| 184. |  |  | Under take street Naming and Property Addressing exercise in 5 communities | 5 selected communities |  |  |  |  |  |  |  |  |  | PPD | Works Department |
| 185. |  |  | Install property address signage | District wide |  |  |  |  |  |  |  |  |  | PPD | Works Department |
| 186. |  |  | Identifying business addresses for capturing/updating revenue database | District Wide |  |  |  |  | 15,500.00 | IGF |  |  |  | PPD | Finance Budget |
| 187. |  |  | Organize SAT and Technical Planning meetings to approve building permits | District Assembly Office |  |  |  |  | 24,000.`00 | IGF |  |  |  | PPD | Lands Commission/TSC/SPC |
| 188 |  |  | Prepare five local plans for fast developing areas | District Assembly Office |  |  |  |  | 170,500.00 | DACF |  |  |  | PPD | TSC/SPC |

| 189. | INFRASTRUCTURE DELIVERY AND MANAGEMENT | SP3.3: SPATIAL PLANNING | Carry out sensitization and educate to improve upon the permitting system | District wide |  |  |  |  | 2,000.00 | GOG |  |  |  | PPD | NCCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 190. |  |  | Reshaping of 36km feeder road | District wide |  |  |  |  | 350,000. | DACF/ IGF |  |  |  | Works Dept. | Central Admin |
| 191. |  |  | Carry out sensitization on road safety measures for Dorkorchiwa GPRTU | Dorkorchiwa |  |  |  |  | 350,000. | DACF/ IGF |  |  |  | Works Dept. | Central Admin |

+

| DEVELOPMENT DIMENSION : EMERGENCY PLANNING AND RESPONSE ( INCLUDING COVID-19 RECOVERY PLAN) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Progr amme (PBB) | Sub- programme (PBB) | Broad Activities | Location | Timeframe |  |  |  | FINANCES (GHC) |  | INDICATORS | Programme Status |  | Implementing Institution/ Department |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | COST | SOURCE |  | New | Ongoing | Lead | Collabo. |
| 192. | P5: ENVIRONMENTAL MANAGEMENT | SP5.1: Disaster Prevention and Management | Awareness creation and sensitization on causes and effects of Fire disasters | In fire prone zones |  |  |  |  |  |  |  |  |  | NADM O | GNFS |
| 193. |  |  | Public Education on Flood, Diseases and Epidemics. | In disaster prone areas |  |  |  |  |  |  |  |  |  | NADM O | DEHU District Health Directorate. |
| 194. |  |  | Education on rainstorm disaster. Identification of flood prone areas. | District wide |  |  |  |  |  |  |  |  |  | NADM O | District Agric Dept. |
| 195. |  |  | International Disaster Risk Reduction Week | Coaltar |  |  |  |  |  |  |  |  |  | NADMO | District Assembly |
| 196. |  |  | Creation & Monitoring of DVGs and activities | District wide |  |  |  |  |  |  |  |  |  | NADMO |  |
| 197. |  |  | Inspection of fuel stations and industries | District wide |  |  |  |  |  |  |  |  |  | NADMO | PPD, WKS, Fin Depts. |
| 198. |  |  | Relief Items Distribution | Any part of the district. |  |  |  |  |  |  |  |  |  | NADMO | DCE/ Central Admin. |
| 199. |  |  | Greening and beautification of the communities | District wide |  |  |  |  | 20,000.00 | IGF/DACF |  |  |  | NADMO | PPD, Agric Dept. |
| 200. |  |  | Sensitizing citizens on climate change, energy | District wide |  |  |  |  |  |  | No. of communities sensitized. |  |  | NADMO | Energy Commission |